PROJECT DESCRIPTION

| Project title: | <insert project title from PPA Art. 4.1> |
| --- | --- |
| Budget Year: | <insert data from PPA Art. 4.4 (a)> |
| Situation(s): | <insert data from PPA Art. 4.4 (b)> |
| Operation: | <insert data from PPA Art. 4.4 (c)> |
| Population Planning Group(s): | <insert data from PPA Art. 4.4 (d)> |
| Goal(s): | <insert data from PPA Art. 4.4 (e)> |
| Cost Centre(s): | <insert data from PPA Art. 4.4 (f)> |
| Partner Code: | <insert data from PPA Art. 4.4 (g)> |
| Project Implementation Period: | <DD-MM-YYYY to DD-MM-YYYY from PPA Art. 3.2> |

- PROJECT OVERVIEW

1.1	Project Statement

This project seeks to contribute to inform the Shelter Cluster response strategy on shelter and non-food items with respect to 850,000 internally displaced persons in Eastern Ukraine through a baseline assessment.

1.2	Operational Context

As a result of ongoing conflict between Ukrainian Government forces and armed opposition groups in the eastern Donbas region of Ukraine, approximately 1.1 million people have been displaced to date from their homes and are becoming increasingly vulnerable as the conflict continues. Of this number, approximately 75% (850.000) are residing in 5 oblasts in the east of the country: Dnipropetrovska, Zaporizka, Kharkivska, Donetska, Luhanska (Source: UNHCR, 11 March 2015), not including the areas currently under the control of armed opposition groups.

Although the Ukraine is a middle income country, the capacity of the government to continue providing services in areas not fully under governmental country is limited. In addition, the ability of the state to rehabilitate infrastructure and shelter has been weakened. In this context, access to basic lifesaving services have been disrupted throughout much of the affected area, with, the influx of displaced persons placing a strain on goods available in the market, resulting in steadily increasing the price of food and non-food items. Since access to cash, income or social benefits may have been disrupted by the displacement the ability of displaced households to meet their needs in a sustainable way may be limited. Moreover, this influx has placed a strain also on the hosting population, in particular in areas with a high ratio of IDPs compared to the local population.

Information on the specific shelter and NFI needs of the displaced population is limited and where available, is not sufficiently representative to be used as the basis of rigorous planning. Although OCHA and ACAPS have recently undertaken assessments with a multi-sectoral focus, these surveys are limited by their broad scope (including just a few key shelter/NFI indicators) and methodology. Data available to the cluster through post-distribution monitoring contains an inherent bias towards existing beneficiaries and therefore cannot by itself be used to build a comprehensive and detailed response plan. That said, REACH recognizes the value of the available data for triangulation of its own findings, and to narrowly define the scope of this assessment in order not to cover ground that has already been covered by others.

In this context, REACH is proposing to undertake a detailed assessment of shelter and NFI needs among the displaced population in Ukraine that is both statistically representative and inclusive of existing data from other assessments and through Ukrainian government agencies. Combining secondary data review (including of OCHA HSM, ACAPS and PDM findings as well as socio-economic data available from the Ukrainian Government) with a robust field data collection method, REACH aims to close the information gap with respect to the shelter and NFI needs of the displaced population and provide a baseline for future assessment activity.

1.3	Problem(s), Objective(s) and Intended Impact

This project seeks to contribute to inform the Shelter Cluster response strategy on shelter and non-food items with respect to 850,000 internally displaced persons in Eastern Ukraine through a baseline assessment. This assessment is designed to provide statistically representative data at the district level to enable the Shelter Cluster to:

1.	Identify priority shelter / NFI needs to be addressed in urban / rural locations across E. Ukraine;

2.	Identify specific vulnerable groups and location types among the overall IDP population;

3.	Understand displacement trends and current intentions of the displaced population

4.	Accurately determine the scale of the response required in Eastern Ukraine and corresponding planning and funding needs to be addressed.

- POPULATION OF CONCERN/OTHER SUPPORTED ENTITIES

The project aims to provide a better understanding of the situation and needs of the displaced population in Eastern Ukraine overall, and does not aim to provide direct protection and assistance to refugees and other persons of concern. Sections 2.1 and 2.2 below are left blank as a result.

2.1	Project’s Population of Concern

The project is aimed at collecting representative data for the entire IDP population in Eastern Ukraine , specifically in the five oblasts Dnipropetrovska, Zaporizka, Kharkivska, Donetska and Luhanska which, not including areas controlled by non-government actors, collectively are hosting approximately 850.000 internally displaced persons. The assessment will take a representative random sample of IDPs in 35 clusters of up between one and up to 17 districts in the accessible areas of Eastern Ukraine, based on official registration data from the Ministry of Social Policy (MoSP) dated 30 March 2015.

By clustering districts into relatively homogeneous groups on the basis of their level of urbanization and population size, economic profile, and geographic location (proximity to the line of contact), the assessment will facilitate programming decisions at a local level whilst avoiding unnecessary duplication at the lowest level. The results will also enable comparative analysis of the different needs of IDPs depending on the type of location in which they have sought refuge, or their distance from the conflict zone.

Moreover, the results will be aggregated to the Oblast and regional level by weighting the results from each district based on the IDP population and thus also enable planning at the regional level. The assessment will be representative at the district-cluster level with a 90% confidence level and a 10% margin of error and at the Eastern Ukraine regional level (95% confidence level with a 5% margin of error).

Using this sampling framework, REACH will target 2,520 households across 135 districts (in 35 clusters) and 5 oblasts:

| Oblast | IDPs | Districts | Clusters (Urban – Rural) | Sample size |
| --- | --- | --- | --- | --- |
| Dnipropetrovska | 71,561 | 35 | 9 (5-4) | 648 |
| Donetska | 407,815 | 27 | 9 (5-4) | 648 |
| Kharkivska | 149,652 | 34 | 7 (2-5) | 504 |
| Luhanska | 143,381 | 14 | 5 (1-4) | 360 |
| Zaporizhka | 81,187 | 25 | 5 (3-2) | 360 |
| Eastern Ukraine | 853,596 | 135 | 35 (16-19) | 2,520 |

2.2	Demographic Data

Since the available demographic data on the age and gender of the displaced population in Eastern Ukraine is limited in its breakdown, this assessment aims to provide a more accurate picture of the overall caseload broken down by age, gender and other key demographic indicators.

2.3	Other Supported Entities

The project aims to support the information requirements of the UNHCR Shelter division, the Shelter and NFI Cluster in Ukraine, implementing partners of each of the aforementioned, and the humanitarian community in Ukraine as a whole. The project aims to assist UNHCR and the Shelter Cluster to better inform the planning, decision making and prioritization of their response overall, by enabling a better understanding of how the location and demographic background of IDPs determine their respective shelter and NFI needs. Moreover the project aims to establish a baseline against which to measure impact through future assessments.

- IMPLEMENTATION ARRANGEMENTS

3.1	Implementation

This assessment will use representative random cluster sampling in order to give a complete picture of the shelter situation and basic NFI needs of IDPs displaced from their homes as a result of the ongoing conflict in eastern Ukraine. The sampling strategy will provide a confidence level of 90% and a 10% margin of error representative geographically at the district cluster level, and will enable generalization of results to the oblast and regional level with a confidence level of 95% and a margin of error of 5%. Moreover the sampling frame will enable disaggregation of the data into two subgroups of urban and rural locations, helping the cluster understand differences based on the local context.

Stage 1: Geographic scope of the assessment

Due to logistical constraints, considering that approximately 75% of IDPs registered by the Ukrainian Government are based in 5 Oblasts in eastern Ukraine (not including areas under control of armed opposition groups), considering that the Shelter Cluster is planning to open a sub-base in Sloviansk to coordinate the response in Eastern Ukraine, the scope of this assessment will be limited to IDPs in these 5 oblasts. For reasons of security, access and the unavailability of basic IDP registration data, the scope of the assessment will be limited to districts currently under governmental control to which enumerators can safely gain access for the purpose of data collection.

Stage 2: Clustering of districts

Following discussions with Shelter Cluster representatives, it became clear that while data that is representative only at the Oblast level would not provide the level of detail required, data representative at the level of the individual district (of which there are 135 within the geographic coverage area) would in fact provide a level of detail that is not necessary to adequately inform the response, and would require a disproportionate investment of time and money. Following discussions between UNHCR and REACH taking into account field experience and lessons learned from post-distribution monitoring, it was agreed to cluster districts into 35 homogeneous units based on the following rules:

•	Clusters are geographically contiguous and do not cross Oblast lines;

•	Individual cities or adjoining urban areas with a population of more than 100,000 inhabitants (2001 census data) form separate clusters;

•	Districts immediately surrounding cities of more than 1 million inhabitants (Dnipropetrovsk and Kharkiv) are clustered separately from other rural areas;

•	Rural districts (and urban districts with a population below 100,000 inhabitants) are clustered based on their proximity to the Line of Contact, creating roughly three rings around the LoC;

•	Districts in the third, most distant ring around the LoC which are located along the main roads between Donetsk and the two major cities Dnipropetrovsk and Kharkiv, are clustered separatedly;

•	The city of Izium (Kharkivska oblast), despite having a population below 100,000 inhabitants, forms a separate cluster due to its unique displacement profile, resulting from previous dynamic in the conflict and location alongside the main road between Donetsk and Kharkiv;

Stage 3: Random selection of households at field level

Within each cluster, a random sample of households representative at the cluster level with a confidence level of 90% and a margin of error of 10% will be selected, geographically spread across the different districts making up the cluster reflecting the ratio of IDP registration in each district. Within each district, target locations will be randomly selected from a list of named towns, villages, settlements and city neighbourhoods in the area. In each location, a total of 8-10 households will be identified and selected for assessment. Households will be selected by enumerators by conducting a field walk, identifying IDP households by asking three different sources for directions: local authorities; local store owners; and so-called babushka’s for directions. After identifying IDPs in the target locations, enumerators will flip a coin to decide whether or not the identified households will be included in the sample. Where possible, interviewed households will also be used to identify further IDP households to assess using the snowball method. Within each cluster, a total of up to 67 households will be assessed, providing a confidence level of 90% and a margin of error of 10% at this lowest unit of measurement.

Where possible, data collection will be conducted using staff seconded by shelter cluster partners to REACH, under the direct supervision of REACH staff for the purposes of this assessment. This will not only present an efficient use of resources, it will also enable REACH to build capacity among local actors and their staff in the robust data collection methodologies applied by REACH. Strengthening such capacity will enable the Shelter Cluster and its partners to apply high data collection and data management standards to their future assessment activities, which for instance may include an assessment of shelter and NFI needs among both IDPs and non-displaced people in the areas not under government control; or assessments studying the impact of planning against targets set based on the baseline dataset produced by this current assessment. Where possible team leaders will be recruited from among the pool of enumerators.

Enumerators will be organized into mobile teams of 4, each with a car and driver (ideally, the driver will also participate in the data collection). Each team will be assigned specific locations to visit within the target clusters. The Field Coordinator and team leaders will accompany the teams to the targeted districts where they will be responsible for introducing the local administrative authorities to the objectives of the assessment to ensure acceptance. Upon arrival in a selected location, the one member of the enumerator team will be responsible for doing the same with local authorities at the town or neighbourhood level. Data collection teams will then, under the supervision of their respective field coordinator, conduct a random selection of 8-10 households per location before moving on to the next location selected for assessment.

All household level assessments will be conducted using an assessment tool built on the KoBo android smart phone based platform. The questionnaire will be conducted in Russian or Ukrainian, based on the preference of the respondent - with enumerators directly entering the answers on the smart phone (procured for the purposes of this assessment by REACH). With exception of open-ended questions, all answers will be immediately available in English for field-level review (spot checks) by REACH Assessment staff and, following upload to the REACH server, will be immediately available in English for analysis.

Completed household survey forms will be first checked and where necessary corrected by the responsible team leader and field coordinator, and will be subject to spot check review by the Assessment coordinator before upload. Answers to open-ended questions will be translated in the resulting database by the Field Coordinators. After translation, the data will be reviewed, any obvious data entry errors excluded from the analysis. Any statistical outliers will be carefully reviewed and either excluded or kept in the analysis as appropriate.

Following the conclusion of data collection, REACH will conduct the initial analysis of the results and will prepare preliminary findings in the form of descriptive statistics for presentation to the Shelter Cluster partners. Results will be statistically representative at the level of the individual targeted clusters, as well as at the level of urban and rural settings across Eastern Ukraine. REACH will be primarily responsible for the analysis, but following presentation of the preliminary results partners are greatly encouraged to provide their feedback and local perspective on these preliminary results, in order to improve the strength and validity of the final analysis. Moreover, partners will be asked following this presentation to provide their input on recommended actions based on the assessment results, for inclusion in the assessment report.

3.2	Risk Management

The planning of the assessment is based on the assumption that certain underlying conditions, dependent on external factors, are and will continue to be met during the period of the project.

- Local authorities will sanction field level data collection;

- Security context will permit REACH teams to safely access the target areas, notably in Luhansk and Donetsk oblasts, for the purpose of household level data collection. REACH will rely on UNHCR and partner organisation security assessment to determine access;

- Shelter Cluster partners will support REACH in the design of the data collection tools by providing input on indicators and questionnaire as well as by supporting the analysis and interpretation of assessment results by providing input on preliminary findings;

In the event that local authorities, security context, logistical constraints or changes in the availability of seconded staff negatively impact the progress of data collection, REACH may in consultation with the Shelter Cluster reduce the sample size in selected locations, thus reducing the confidence level, in order to achieve results on a timely basis.

In the absence of local partners to second staff in these areas, REACH enumerators will in any case be responsible for covering the area of Kharkiv, Dnipropetrovska and Zaporizhka oblasts. UNHCR will request partner organisations to provide staff to cover Donetska and Luhanska oblasts. If no partner can commit to conduct data collection in these areas by 10 April at the latest, REACH will recruit its own enumerators to cover the gap.

In the event that sufficient seconded staff resources are available, REACH enumerators may in consultation with the Shelter Cluster be allocated to either cover areas where partners have no presence, or increase the sample size in selected locations, thus improving the confidence level and reducing margin of error of findings. This, however, may require realignment of budget lines as the operational framework changes.

- Secondary data is shared, where possible in English, by relevant parties;

The REACH assessment coordinator will work closely with the Shelter Cluster Coordinator to ensure all available data are shared.

- The project is approved and funded by UNHCR in a timely manner

The production of project deliverables in time for the information to feed into the SRP Review envisaged for the end of May, may be dependent on the timely approval of the PPA. The REACH Assessment Coordinator will share preliminary results at an as early stage as possible to enable this data to inform time-sensitive decisions.

3.2	Coordination

The development of the indicators to be measured by the assessment and the design of the questionnaire, including its translation to Russian and Ukrainian, will take place in close consultation with the Shelter Cluster Coordinator.

The analysis and interpretation of the primary data collected by the field teams will also take place in close consultation not only with the Cluster Coordinator, but also with implementing partners of the cluster in order to reflect their field level experience and perspectives.

3.3	Review and Reporting

Progress of activities will be reviewed and reported against indicators on a monthly basis. This will be shared with UNHCR. ACTED’s programme development and reporting department will report back to UNHCR in accordance with contractual requirements and deadlines.

The assessment will result in the publication of a final assessment report, including an executive summary, as well as static analytical maps. The report and accompanying maps will be validated by the Shelter Cluster lead in Ukraine and the REACH global headquarters in Geneva before publication. This report will be targeted to local and international Shelter Cluster partners, other humanitarian actors as well as other interested parties. The report will be disseminated in Ukraine by the Shelter Cluster, and may be disseminated to international partners by the Shelter Cluster and REACH as appropriate.

Moreover, REACH will provide a Powerpoint presentation of key findings for the purpose of sharing with partners by the Shelter Cluster.

Finally, REACH will hand over all raw data as well as a cleaned dataset (with any personal identifying information such as names, addresses or phone-numbers of beneficiaries removed) of the household survey results with the Shelter Cluster. Data will be handed over to UNHCR IM for matching with existing data sets and shape files. All mapping and reports are shared, upon approval from UNHCR, to cluster working groups and other stakeholders.

3.4	Visibility

All documents for public or limited internal sharing resulting from the assessment, including the report, static maps and any summary of preliminary findings to be circulated, shall carry UNHCR and Shelter Cluster logos but shall adhere to REACH graphic standards.

3.5	Other

Not applicable.

- RELATED INPUTS AND PROJECTS

4.1	Partner

Not applicable.

4.2	Other Parties

Shelter Cluster partners have been requested to contribute staff resources for the purposes of data collection. While some partners have indicated an interest in doing so, no formal arrangements or agreements have been made. In the event that such resources do become available, Impact and UNHCR will discuss the best way forward regarding the use of such resources, which may or may not include increasing the sample size or expanding the geographic scope of the assessment.

- AGREEMENT AMENDMENT HISTORY

Not applicable.

- PLANNED RESULTS

| Results Chain |  |  |  |  |
| --- | --- | --- | --- | --- |
| Population Planning Group: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| Goal: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| Rights Group: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| <The table below is repeated for each Problem – Objective>. |  |  |  |  |
| Problem Analysis ~ Objective |  |  |  |  |
| Problem Name: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| Problem Description: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| Objective Name: | <Mandatory. Completed by UNHCR from Operations Plan.> |  |  |  |
| Intended Impact: | <Mandatory. Completed by UNHCR from Operations Plan narrative adjusted to the scope of the project.> |  |  |  |
| Impact Indicator(s) |  |  |  |  |
| Impact Indicator Name | Impact Indicator description | Site/Location | Impact Indicator Baseline | Impact Indicator Target |
| <Mandatory. Completed by UNHCR from Operations Plan.> | <Mandatory. Completed by UNHCR from Operations Plan.> | <Mandatory. Completed by UNHCR.> | <Mandatory. Completed by UNHCR from Operations Plan.> | <Mandatory. Completed by UNHCR from Operations Plan adjusted to for the project.> |

<The table below is repeated for each Output>.

| Agreed Output(s) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output(s) Name | Brief description of the Output | Site/Location | Performance Indicator(s) | Performance Target(s) | Budget Target |
| <Mandatory. Completed by UNHCR. There must be at least one output based on the Operations Plan with all related indicators included.> | <Several Performance Indicators can be used for an output. Describe the main activities supporting the output.> | <Mandatory. Completed by UNHCR from Operations Plan.> | <Mandatory. Completed by UNHCR from Operations Plan.> | <Mandatory. As jointly agreed with UNHCR and partner for the project> | <Total budget for the output as per Project Budget (Annex B).> |
|  |  |  | <Optional. Custom indicator agreed by UNHCR and partner> | <Optional. Custom indicator agreed by UNHCR and partner> |  |
| <Optional and conditional on partner fully funding the output. Set by partner for custom indicators> | <Described by partner for custom indicators> | <Set by partner for custom indicators> | <Set by partner for custom indicators> | <Set by partner for custom indicators> | <Total budget for the output funded by the partner> |