| Research Terms of Reference Joint Market Monitoring Initiative (JMMI) SDN2303 Sudan |  |
| --- | --- |
| December 2025 V3 |  |

# Executive Summary

| Country of intervention | Sudan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Emergency | □ | Natural disaster | X | Conflict |  |  | □ | Other (specify) |  |
| Type of Crisis | □ | Sudden onset | □ | Slow onset |  |  | X | Protracted |  |
| Mandating Body/ Agency | Sudan Cash Working Group & Minimum Expenditure Basket (MEB)Task Force |  |  |  |  |  |  |  |
| IMPACT Project Code | SDN2303 |  |  |  |  |  |  |  |
| Overall Research Timeframe (from research design to final outputs / M&E) | Monthly (ongoing), started in December 2023. |  |  |  |  |  |  |  |
| Research Timeframe Add planned deadlines (for first cycle if more than 1) | 1. Pilot/training: 1-4/12/2025 |  |  |  | 4. Data analysed and validated in-country: 31/12/2025 |  |  |  |
|  | 2. Start collecting data: 04/12/2025 |  |  |  | 5. Outputs published: 10/01/2025 |  |  |  |
|  | 3. Data collected: 14/12/2025 |  |  |  |  |  |  |  |
| Number of assessments | □ | Single assessment (one cycle) |  |  |  |  |  |  |
|  | X | Multi-assessment (more than one cycle) Monthly cycle |  |  |  |  |  |  |
| Humanitarian milestones Specify what the assessment will inform and when e.g. The shelter cluster will use this data to draft its Revised Flash Appeal; | Milestone |  |  |  | Deadline |  |  |  |
|  | □ | Donor plan/strategy |  |  | _ _/_ _/_ _ _ _ |  |  |  |
|  | X | Inter-cluster plan/strategy |  |  | TBD |  |  |  |
|  | X | Cluster plan/strategy |  |  | Ongoing |  |  |  |
|  | X | NGO platform plan/strategy |  |  | Ongoing |  |  |  |
|  | □ | Other (Specify): |  |  | _ _/_ _/_ _ _ _ |  |  |  |
| Audience Type & Dissemination: Specify who will the assessment inform and how you will disseminate to inform the audience | Audience type |  |  |  | Dissemination |  |  |  |
|  | □ Strategic X Programmatic X Operational |  |  |  | X General Product Mailing (e.g. mail to NGO consortium; HCT participants; Donors) X Cluster Mailing (CWG) and presentation of findings at the next cluster meeting. X Presentation of findings (e.g. at HCT meeting; Cluster meeting) X Website Dissemination (Relief Web & REACH Resource Centre) |  |  |  |
| Detailed dissemination plan required | □ | Yes |  |  | x | No |  |  |
| General Objective | Informing the Sudan Cash Working Group and other cash actors about developments in prices and market functionality across Sudan in the face of renewed conflict since April 15th, 2023, and provide an evidence base to inform the design, implementation and appropriate adjustments in cash and voucher assistance (CVA). |  |  |  |  |  |  |  |
| Specific Objective(s) | - Track prices and availability of basic commodities in Sudan, with a particular focus on food and NFI items(household items and hygiene items) - Assess the impact of conflict, seasonality, and inflation on the functionality and accessibility of key market systems - Contribute to a broader understanding of the market environment |  |  |  |  |  |  |  |
| Research Questions | - What are the prices and availability of basic food and non-food items in markets throughout Sudan, and how do these vary over time and based on payment modality? - What are the costs associated with the Minimum Expenditure Basket (MEB) for Sudan? - What are the geographical price variations and trends for these basic items over time? - What is the availability of these commodities? - What are the available payment modalities for these basic items and how does the price change based on the chosen modality? - What are the current exchange rates for major currencies, especially the US dollar, against the Sudanese pound in local markets? - To what extent can assessed markets currently be considered functional, based on the five dimensions (accessibility, availability, affordability, resilience, and infrastructure) of the REACH Market Functionality Score? - Do all market actors, including customers, have physical/social/ access to markets? - Are the prices for core items stable in this market? - Can vendors reliably provide all core items that local households need to purchase on a regular basis? - Do customers have financial access to markets? - Do supply chains for core items market function reliably? - Is the physical infrastructure in and around markets (buildings, roads, etc.) in sufficiently good condition to support normal livelihood and trading activities? Do vendors have access to locked, secure storage facilities where they can keep their stock? - What are the main supply chain pathways for basic food and non-food items in different regions of Sudan? - How resilient are these supply chains to shocks such as conflict, seasonality, and inflation? - How does the functionality of these supply chains affect the availability and price of basic food and non-food items in local markets |  |  |  |  |  |  |  |
| Geographic Coverage | Aims to achieve nationwide coverage across all 18 states of Sudan. The specific areas surveyed each month will be determined based on partner support and capacity. |  |  |  |  |  |  |  |
| Secondary data sources | - WFP food price data - Reliefweb country SDN - IPC Sudan Acute Food Insecurity IPC country analysis - CALP network publications - Documents shared by the CWG, including assessments and analyses conducted by partners. These include: - Market System Strengthening Assessment (MSSA) Chad-Sudan cross-border trade may, 2025 - CCS - Private Sector Engagement in Cash Distributions - Impact Sudan published resource |  |  |  |  |  |  |  |
| Population(s) | □ | IDPs in camps |  |  | X | IDPs in informal sites |  |  |
| Select all that apply | X | IDPs in host communities |  |  | □ | IDPs [Other, Specify] |  |  |
|  | □ | Refugees in camps |  |  | □ | Refugees in informal sites |  |  |
|  | □ | Refugees in host communities |  |  | □ | Refugees [Other, Specify] |  |  |
|  | X | Host communities |  |  |
| Stratification Select type(s) and enter number of strata | X | Geographical #: TBD based on partner coverage Population size per strata is known? □ Yes X No | □ | Group #: _ _ _ Population size per strata is known? □ Yes □ No |  |  | □ | [Other Specify] #: _ _ Population size per strata is known? □ Yes □ No |
| Data collection tool(s) | X | Structured (Quantitative) |  |  | □ | Semi-structured (Qualitative) |  |  |
|  | Sampling method |  |  |  | Data collection method |  |  |  |
| Structured data collection tool # 1 Select sampling and data collection method and specify target # interviews | X Purposive □ Probability / Simple random □ Probability / Stratified simple random □ Probability / Cluster sampling □ Probability / Stratified cluster sampling X Snowball sampling |  |  |  | X Key informant interview (Target #): 4-5 vendors per monitored item, max 30 forms per assessed area (Admin 2). (dependent on partner capacity and resources). □ Group discussion (Target #):_ _ _ _ _ □ Household interview (Target #):_ _ _ _ _ □ Individual interview (Target #):_ _ _ _ _ □ Direct observations (Target #):_ _ _ _ _ □ [Other, Specify] (Target #):_ _ _ _ _ |  |  |  |
| Target level of precision if probability sampling | N/A |  |  |  | N/A |  |  |  |
| Data management platform(s) | X | IMPACT |  |  | □ | UNHCR |  |  |
| Expected ouput type(s) | □ | Situation overview #: _ _ | □ | Report #: _ _ |  |  | □ | Profile #: _ _ |
|  | □ | Presentation (Preliminary findings) #: _ _ | X | Presentation (Final) #: 1 per round or as requested |  |  | X | Factsheet #: 1 per round except February 2026 |
|  | □ | Interactive dashboard #:_ | □ | Webmap #: _ _ |  |  | □ | Map #: _ _ |
|  | X | Dataset #: 1 per round |  |  |  |  |  |  |
| Access | X | Public (available on the REACH resource centre and other humanitarian platforms) |  |  |  |  |  |  |
|  | □ | Restricted (bilateral dissemination only upon agreed dissemination list, no publication on REACH or other platforms) |  |  |  |  |  |  |
| Visibility: Specify which logos should be on output | REACH |  |  |  |  |  |  |  |
|  | Donor: ECHO & GoS |  |  |  |  |  |  |  |
|  | Coordination Framework: CWG & MEB TF |  |  |  |  |  |  |  |
|  | Partners: Partners participating in data collection will be listed on the data analysis sheet, presentations and factsheets, but partner logos will not be included. |  |  |  |  |  |  |  |

# Rationale

  - Background

On 15 April 2023, conflict ignited between the Sudanese Armed Forces SAF and the Rapid Support Forces RSF across the country. As of September 2025, the conflict between the SAF and RSF has escalated into a protracted and devastating nationwide war, plunging Sudan into the world's most severe humanitarian and displacement crisis. According to the latest IOM Displacement Tracking Matrix DTM Sudan Mobility Update March 23, 2025, the number of internally displaced persons IDPs has surged to 10.5 million, while cross-border refugee movements have reached nearly four million across borders into neighbouring countries, including Egypt, South Sudan, Chad, Ethiopia, Libya, the Central African Republic and others marking a drastic deterioration since the conflict began.

The food security situation has continued to decline catastrophically. Sudan risks becoming the world’s largest hunger crisis in recent history as conflict continues to rage, destroying livelihoods, infrastructure, trade routes and supply chains. An estimated 21.2 million are facing high levels of acute food insecurity, according to the latest Integrated Food Security Phase Classification. The IPC June 2024 initially projected that 17.7 million people would face Crisis IPC Phase 3 or worse acute food insecurity during the 2024 lean season. The Acute Food Insecurity Snapshot June 2024 indicates that approximately 24.6 million people across Sudan will likely experience high levels of acute food insecurity IPC Phase 3 or above between December 2024 and May 2025. This includes 8.1 million people in IPC Phase 4 (Emergency) and at least 638,000 people in IPC Phase 5 (Catastrophe). Conditions are pervasive across conflict hotspots, including Khartoum, Darfur, and Kordofan. Famine-like conditions are likely present in several hard-to-reach areas, particularly in North Darfur and among IDPs in camp settings. However, limited humanitarian access continues to obstruct complete verification.

The macroeconomic collapse has continued unabated through mid-2025. Annual inflation is projected to remain hyperinflationary, consistently exceeding 380% throughout the first three quarters of 2025, while the Sudanese Pound SDG has hit successive record lows against the US dollar on parallel markets.  This economic meltdown, synergised with a perpetual nationwide liquidity crisis and the near-total disruption of key inter-state supply routes, has shattered market functionality. The fragmentation into isolated, volatile regional subsystems has intensified, with each subsystem facing its own severe access constraints and wildly fluctuating prices. Households' total dependence on these fractured markets for survival has been solidified, while their ability to access goods and cash physically has further diminished.

In this context, the need for a coordinated, multi-sectoral market monitoring system has never been more critical. Since October 2023, the Joint Market Monitoring Initiative (JMMI), co-led by IMPACT and the Sudan Cash Working Group (CWG), monitors all relevant food and non-food items commodities included in the Minimum Expenditure Basket (MEB), and has adapted continuously to these escalating challenges, also enhancing CWG partners’ coordination to ensure a coverage expansion throughout the years. Since 2023, JMMI data have been instrumental in facilitating quarterly transfer value adjustments by the MEB taskforce and major cash consortium, ensuring assistance levels remain commensurate with soaring inflation and market volatility.

Despite these efforts, significant information gaps persist, particularly in hard-to-reach areas such as Khartoum, Darfur, and Kordofan, where systematic price monitoring remains inconsistent. The JMMI intends to fill this gap by harmonizing data collection across CWG partners, enhancing partners coordination, thus providing a unified evidence base that directly informs Cash and Voucher Assistance (CVA) programming.

  - Intended impact

Since the launch of the Joint Market Monitoring Initiative (JMMI) in 2023, data collection efforts have been successfully consolidated and critical information gaps across Sudan have been addressed. The initiative consistently supplements existing monitoring mechanisms by providing robust data on previously underrepresented areas, most notably through the systematic tracking of food and Non-Food Item (NFI) prices and market functionality outlook. This holistic and evidence-based approach directly enables the expansion and adaptation of Cash and Voucher Assistance (CVA) programming, ensuring an informed and effective response, aligned with the evolving realities on the ground, ultimately improving the dignity and purchasing power of crisis-affected populations.

# Methodology

  - Methodology overview

The activity outlined in these terms of reference (ToR) is designed to provide longitudinal market and price data using REACH’s JMMI methodology, which has been rolled out in 20 countries to date. The initiative, to be conducted in partnership with the Sudan CWG, will be coordinated through a CWG or MEB TF JMMI Taskforce established for this purpose, which will be co-led by REACH and the CWG. On behalf of the taskforce, REACH will develop the research design, data collection tools, guidance documents, training materials, datasets, analysis, and outputs for the JMMI, as well as draft the ToR for the taskforce itself, all with iterative input from taskforce members. The taskforce members, in turn, will work to develop their own key informant (KI) networks, coordinate the coverage of the assessment, collect data, and review or endorse all aspects of the research design, as well as potentially take on some aspects of the training and data cleaning if capacity allows. REACH will aim to complete data collection in sites not covered by other JMMI members as its own capacity allows.

Data collection will be a joint, partner-led exercise carried out by CWG members using a harmonised questionnaire. The methodology centres on quantitative, structured interviews with purposively sampled traders who will act as KIs for their respective markets. Partners will focus on interviewing retailers, rather than wholesalers or distributors, as these are the market actors most likely to sell to the vulnerable populations that humanitarian actors generally target. Data collection is scheduled to launch the first week of the month, with data being collected, cleaned and analysed on a monthly basis. Outputs will include data analysis tables and a factsheet summarising key findings every month.

  - Population of interest

The JMMI provide rapid information on prices and market functionality to humanitarian actors working throughout Sudan, both in areas directly affected by conflict and in those affected by the IDP influx. The geographical coverage of the exercise will depend on the access of JMMI taskforce members to markets and their ability to collect data from these areas on a consistent basis.

The unit of analysis for this assessment will be at the Admin 2, or district/locality level. This is informed by the fact that admin 3 level data is currently unavailable, hence limiting the feasible granularity of the analysis. Furthermore, districts are the standard unit of analysis in Sudan according to OCHA and the Integrated Food Security Phase Classification (IPC). Districts serve as crucial nodes for trade and commerce, typically embodying areas of high population density, including displaced populations, and are administrative units where policy and programme interventions can be effectively implemented and monitored. Adopting a district-level analysis allows for the differentiation of market dynamics within and between districts. This level of granularity is crucial for understanding how to tailor CVA strategies in diverse contexts, ensuring alignment with existing administrative and data structures, thereby promoting the harmonization and effectiveness of the assessment.

  - Secondary data review

| Source | Use |
| --- | --- |
| REACH Assessments: - Existing market data from REACH Sudan - Other JMMIs – South Sudan & Ethiopia, for example, Supply Chain Analysis | Broader contextual understanding, including the use of regional products to inform cross-border dynamics relevant to aspects of market functionality. |
| WFP's Food Security Analysis (VAM) | Provides updated data and analysis on food security and markets in Sudan, aiding in understanding the context, identifying information gaps, and triangulating primary data. |
| IOM Displacement Tracking Matrix (DTM) & UNHCR Population Statistics Reference Database | Offer detailed information on displacement in Sudan, informing the sampling design and contextualizing the assessment. |
| Sudan Cash Working Group (SCWG) reports, meeting notes, etc | Provides updates and insights into any knowledge gaps or implementation issues. |
| Sudan Humanitarian Needs and Response Plan 2025 - Executive Summary (December 2024) ¦ OCHA | Provides the most recent overview of the humanitarian situation in Sudan, including information on priority needs and response strategies. |
| Rapid Assessments from partners/NGOs operating in Sudan | These sources provide valuable context and help identify information gaps. Helps to avoid duplication. |

  - Primary Data Collection

Coordination

The JMMI is a joint exercise led by REACH and the CWG, in close collaboration with the JMMI Taskforce members, who voluntarily collect data from their respective areas of operation. As such, the scope and coverage of the JMMI will largely depend on the interest and capacity of JMMI Taskforce members. The JMMI Taskforce will serve as the decision-making body guiding the initiative. The objective of this Taskforce is to support the successful implementation of the JMMI and to build technical consensus among participating members.

The JMMI Taskforce will be co-led by REACH and the CWG, and all partner organisations contributing to the initiative are counted as members. The Taskforce agrees to adopt a common approach toward the key pillars of the initiative, including methodology, data collection tools, item lists, coverage, visibility, and ownership of data.

Methods

All data for the JMMI will be collected by member organizations of the JMMI Taskforce on a monthly basis using a structured quantitative tool. Data will be collected in the form of key informant interviews (KIIs), with retailers in target markets serving as the KIs. In accordance with the “joint” methodology of the JMMI:

- All partners will commit to supporting one joint monitoring process.

- All partners will use the same data collection tools.

- All partners will use the same data collection methodology.

- All partners will commit to attending the training conducted by REACH.

- All partners will collect data during the same period determined by REACH.

- All partners will upload their data to the same KOBO server.

- All partners will commit to supporting the data cleaning process through their feedback.

Collectively, taskforce members will aim to cover as broad a selection of markets in districts across Sudan as possible, with a focus on urban markets and those serving the most significant number of persons of concern. In practice, maximally broad coverage will need to be achieved via a process of “deconfliction”:

- Each participating organization begins by proposing all districts/markets from which it could commit to collect data based on the locations of its field bases.

- REACH and CWG, as the co-leads of the JMMI task force, compare the organizations’ potential areas of coverage, resolve any overlaps, and suggest modifications to ensure that organizations are not duplicating each other’s work.

In some cases, REACH and CWG may propose that these organizations cover neighbouring localities instead of those that would not otherwise be incorporated.

Sampling

Sampling Frame

Given the collaborative nature of this assessment, where coverage depends on the interest of partner organisations and their field teams' capacities to collect market data regularly, the number of markets included in the assessment may vary between months. However, the following minimum standard will be used to ensure diversity of coverage, indicative representation, and that the assessment conforms to prevailing statistical benchmarks.

Considering the complexity and diversity of marketplaces in Sudan, the assessment will aim to survey a minimum of 50 marketplaces each month to ensure the representation of various economic realities. This number offers a balance between statistical rigour, representation of diverse marketplaces, and practicality in terms of partners' capacities. However, due to the sampling approach, it is important to note that findings for this assessment are indicative only.

In each surveyed marketplace, at least four retailers per assessed item category (e.g., food items, non-food items) should be interviewed, with a maximum of 30 forms per district (Admin 2) submitted on a monthly basis. This will help with data triangulation, ensuring multiple data sources for reliable results and aid in mitigating the impact of potential outliers.

Overall, this culminates in a minimum of 200 retailers surveyed each month. These figures, however, remain flexible to accommodate partners' capacities and evolving ground realities. The final sampling frame will be subject to continual reviews and adjustments in accordance with the interests, commitments, and capacities of our partner organisations and their field teams.

Marketplace selection:

The JMMI will initially prioritise marketplaces in locations directly and indirectly affected by the conflict. For the purposes of the JMMI, a marketplace is defined as an area with a relatively sizable concentration of traders in close proximity to each other. These traders can be located in a devoted market area, in a central business district, along a commercial corridor, or similar areas. This vague definition is designed to encompass a wide variety of marketplaces that enumerators may encounter in the field and to enable each organisation to make judgments about the most valuable ones to monitor based on local realities. Field teams within each participating organisation are responsible for identifying the main markets in each targeted garrison district that meet this definition.

Taskforce members who have committed to collecting data from a particular locality should, in general, target traders from the locality’s largest retail marketplaces (i.e., not targeting markets that are exclusively for wholesalers, etc.). In locations where markets are relatively well-integrated and where the same goods tend to flow from central markets outwards to peripheral areas, simply interviewing traders from the district’s main marketplaces should provide a sufficiently indicative overview of market conditions throughout the target area.

Only one partner should contribute data from each monitored district (Admin2) per round. For a smaller state (Admin1), one partner will be assigned to cover the area. For a larger state, the JMMI task force will determine the best way to divide the area into smaller sections that will be assigned to one partner.

Trader selection:

Within each targeted marketplace, field teams within each participating organisation are responsible for identifying a maximum of 30 traders to interview that match the following criteria:

- Traders must be retailers selling directly to consumers. Wholesalers should be avoided unless they also commonly sell directly to consumers; in this case, only their consumer retail operations should be assessed.

- Traders must sell at least one item monitored as part of the JMMI survey; preferably, they will sell as many of these items as possible.

- Enumerators should aim to monitor the same traders or types of traders patronised by average consumers in the area. Traders selling upmarket goods and expensive brands that are not purchased by most households should be avoided.

- Traders with weight scales should be prioritised for food items. However, traders without weight scales may be interviewed as well if there are not enough traders with scales in the marketplace.

- To the extent possible, traders should be located in different parts of the marketplace. There are no restrictions on the size of the surveyed traders, as consumers typically buy from both small and large traders.

Field teams must aim to collect a minimum of 4 prices (if the context allows) per assessed item per assessed locality, ideally all from the district’s largest and most central marketplace. To ensure data quality and consistency, field teams should aim to interview up to 30 retailers per market. This sample size is designed to facilitate efficient data cleaning and minimize errors by providing a robust dataset. Teams must continue interviewing retailers until they have collected at least four prices for every assessed item. If the initial 30 forms are insufficient to achieve this minimum price coverage for all items, teams must notify the JMMI coordination team to agree on whether to continue data collection until the requirement is met.

Field teams should continue interviewing traders until they have collected the minimum number of prices for every assessed item, if possible. If an enumerator is able to collect every required price via visits to 4 large general stores, then they will only need to interview four traders in that market; if they collect prices primarily from small-scale traders that sell only a few items each, the number of interviews will be higher (but each individual interview will be much shorter). If an item is only sold by 1-3 traders in the location, field teams may collect data only from these traders and inform their field coordinators of the situation. If an item is never sold in a specific location or is seasonally or otherwise unavailable across the entire area, no price data for this item needs to be collected. However, the enumerator should note these dynamics in the comments section of the data collection tool.

When approaching a given trader for the first time, the enumerator should begin by introducing themselves and their organisation, clearly explaining the purpose and nature of the assessment and the amount of time they expect the survey to take to complete, and should confirm whether the vendor is willing to contribute information to the assessment every month. If the vendor agrees, the enumerator should strive to collect data from that vendor in every round as far as possible and should continue to confirm at the beginning of each survey that the vendor consents to continue participating however, if a particular trader is consistently reporting prices that are far out of step with other vendors in the same marketplace, whether because they are generally expensive or because they are potentially inflating reported prices in the hope of benefiting from humanitarian programming, this trader should be avoided in future rounds and replaced with another.

Items to monitor

As part of the JMMI, all participating organisations will monitor the prices of an agreed list of items. Members of the CWG and MEB TF will negotiate the contents of this basket among themselves, but they will be mainly based on the contents of the MEB for Sudan. The JMMI Taskforce may choose to include additional items of interest to Food Security and Livelihoods (FSL), Shelter and Non-Food Items (SNFIs), Nutrition, Water, Sanitation and Hygiene (WASH), Protection, Health, and other clusters.

In instances where items in the basket are commonly sold in several different varieties, data will be collected on only the cheapest commonly consumed variety available in the marketplace, in line with the purpose of the Minimum Expenditure Basket. While this is a straightforward process for most food items, non-food items (NFIs) tend to be more complicated to standardise, as they can vary significantly in terms of types and specifications. For consumable NFIs (i.e. those that are continually used up and need to be repurchased, such as soap, toothpaste, cleaning products, etc.), enumerators should follow the procedure of only collecting the price of the cheapest variety. For non-consumable NFIs, such as plastic sheets or buckets, the JMMI Taskforce agreed on a list of loose specifications for each item to ensure that all partners are monitoring comparable commodities.

Table 1: Composition of the JMMI item list

| Type | Item |
| --- | --- |
| Food | Sorghum |
| Food | Onions |
| Food | Vegetable oil |
| Food | Milk (fresh) |
| Food | Cow meat (fresh) |
| Food | Goat meat (fresh) |
| Food | Dried tomato |
| Food | Sugar |
| Household | Gas Cylinder |
| Household | Gas Refill |
| Household | Water container |
| Household | Water supply |
| Hygiene | Body soap |
| Hygiene | Toothpaste |
| Hygiene | Toothbrushes (adult+children) |
| Hygiene | Laundry soap |
| Hygiene | Liquid dish soap |
| Hygiene | Sanitary pads |

The JMMI item list is monitored across all covered locations to address the interests of CWG partners. This list includes a selection of commodities that are part of the Minimum Expenditure Basket (MEB), along with additional items relevant to WASH, shelter, and non-food items (NFI). The items included are Sorghum, Onions, Vegetable oil, Fresh milk, Fresh cow meat, Fresh goat meat, Dried tomatoes, Sugar, Gas cylinders, Gas refills, Water containers, Water supply, Body soap, Toothpaste, Toothbrushes (both adult and children's), Laundry soap, Liquid dish soap and Sanitary pads.

The JMMI Technical Working Group (TWG) established the current item list in July 2019, and it is subject to adjustments in future rounds based on the needs of the Cash Working Group. Regarding the MEB list, this ability to modify the items depends on the need of the CWG. Occasionally, security authorities may request the removal of certain questions. Instead of halting the assessment, they can specify which questions to delete, and we will ensure that those questions are omitted for the affected area.

Data Collection Tool

All data collection for the JMMI will centre on the KOBO platform. Once the basket of monitored items has been finalised, REACH will update the standard quantitative data collection tool in KOBO for use in the JMMI, to be hosted on a centralised KOBO server owned by REACH. All data must be uploaded to the JMMI Taskforce’s central KOBO server using one of two Android apps (KOBO Collect or ODK Collect) or, alternatively, using a link that can be filled out in one’s internet browser. Enumerators using either Android app will be able to complete surveys without an internet connection and save them for later submission once they return from the field. Partner organizations are responsible for providing their enumerators with all necessary equipment (smartphone/tablet, laptop, internet connection) to enable them to undertake data collection.

All Taskforce members participating in the initiative are asked to submit their data using this standard KOBO tool, unless circumstances wholly prevent them from doing so. In such cases, an individualised plan can be worked out with each participating organisation.

PDF versions of the questionnaire can be provided on an ad hoc basis for enumerators who prefer to collect data on paper in the field. The enumerators will be responsible for printing and transporting these questionnaires themselves. However, filling out a paper form is not a substitute for submitting data to the central KOBO server. All data collected on paper must subsequently be uploaded to KOBO by the enumerators themselves by the end of each day of data collection, or at the latest by the end of the data collection period, just as if they were collecting data using an Android app. No extensions to the data collection period will be provided for this purpose; therefore, partners and enumerators must plan ahead for the additional time required for data entry.

Unit Standardisation

If the trader owns a scale, the price per kilogram is recorded. Traders with weight scales should be prioritised, and traders without scales should be avoided if others in the marketplace own one. To accommodate contextualised measurement of certain goods (where relevant), prior to data collection, the JMMI Taskforce provides standardised conversion factors to field teams. These conversions ensure alignment between local units reported by traders and the standardised units used for analysis. To accommodate contextualised measurement of certain goods (if relevant), prior to data collection, the JMMI Taskforce will request measurement conversions between these measurements and the standard measurements that will be used for analysis purposes.

  - Data Processing & Analysis

Data cleaning

Following each round of data collection, REACH will compile the centralised, raw data, remove outliers, and follow up with field teams if needed. Data cleaning will be an ongoing process, conducted daily during the data collection phase, enabling proactive adjustments and minimising the replication of errors. For further information, see IMPACT’s Data Cleaning guidelines and Data Cleaning Checklist.

In particular, the data will be checked for the following:

- Number of prices per item collected per location (to check if the minimum threshold of 4 prices per item has been met)

- Median price per item per location (to check for variation across locations)

- Minimum and maximum price per item per location (to check for variation within locations)

- Outliers (i.e. an item price that is substantially different from others collected in the same month and location)

- Monthly changes in the median price per location (to check for month-on-month variation)

  - Significant price changes (exceeding 50% since the previous month) and sudden shortages are further investigated by following up with field teams. Whenever possible, information about the local context is gathered to support the analysis.

- GPS coordinates of entries (to check the legitimacy of submitted data)

- Duration of surveys per location (to check the legitimacy of submitted data)

Following each round of data collection, REACH assessment staff triangulate the obtained data through three different steps:

- Comparison of the most recently collected data with previous rounds of data to identify inconsistencies.

- Review of secondary data covering the same location(s), if any.

- Consultation of field teams and partners to cross-check data quality and contextualise results.

Data analysis

The primary software used for performing the data analysis will be R programming, where daily data cleaning is carried out through Microsoft Excel to treat logical checks that flag potential errors, for review and adjustment. After the corrections have been made, the updated data will be re-evaluated in R using a customized R package to confirm the adjustments. This process ensures that the final clean dataset generated in R is both accurate and reliable for further analysis.

As the data is collected on the key informant level, the following steps are undertaken to aggregate the trader level data onto the different location levels (that is, district and state levels):

- Availability: Availability is defined categorically (available, limited, unavailable) for each item based on the following logic:

  - If an item is available as normal from at least one surveyed trader, it is considered available in the district.

  - Else: If an item is not available as normal from any surveyed trader but is available on a limited basis from at least one trader, it is considered to have limited availability in the district.

  - Else: If an item is not available either on a normal or a limited basis from any surveyed trader, it is considered to be unavailable in the district.

- Prices: Using prices collected from individual traders, median prices are calculated for each item within each assessed district. State medians are then calculated using a “median of medians” approach, i.e. by taking a second median across all the district-level medians in a particular state.

- Stock levels: For each item, the median stock level is calculated across all surveyed traders in the district. State medians are then calculated using a “median of medians” approach, as above.

- Ability to restock: If at least one trader is able to restock an item, the district-level aggregate will be “yes”, else “no” (if the item is normally not sold at all).

- Restocked in the last month: If at least one trader restocked an item in the last month, the district-level aggregate will be “yes”, else “no”.

- Restock duration: The median restock duration across all traders in the district is calculated for food and non-food items.

- Location of food/NFI supplier: The most commonly named location is taken as the location of the district’s main suppliers for each category of monitored items. If no clear location is commonly reported, all locations that were equally commonly reported will be presented.

A second aspect of the data analysis process will involve the integration of an internally developed Market Functionality Score (MFS). The MFS is a method developed by REACH, intended to classify markets based on their functionality levels. This classification facilitates comparisons both within and among countries, providing invaluable insights for aid actors. The knowledge gleaned from these comparisons helps determine which markets are viable for Cash and Voucher Assistance (CVA) and which markets necessitate alternative forms of Market-Based Programming (MBP) to achieve self-sufficiency.

The MFS comprises a suite of indicators drawn from a singular, vendor-focused assessment. This design simplifies the analysis process while capturing various dimensions of market functionality. The indicators cover a range of dimensions, including:

- Physical, financial, and social accessibility for all groups, including security aspects.

- Availability and affordability of essential market commodities.

- Resilience of key supply chains to disruptions.

- Infrastructure issues, including those affecting the transportation of goods.

Each dimension and indicator are assigned specific weights and thresholds, reflecting their influence on the market's overall capacity to meet customer demand. Thus, the integration of the MFS into the methodology of this assessment will enhance the understanding of market dynamics and the feasibility of CVA as an appropriate response for crisis-affected communities.

Weighting the Indicators

Each indicator that forms the MFS will be weighted by setting a maximum score for each based on its relative importance within its dimension. To do this, the team will first identify the specific values or answer options for each indicator that reflect the best and worst situations with regard to market functionality, following a discussion of what each indicator and potential response might mean given the current socioeconomic context in Sudan. A set of suggested standard indicators and thresholds is provided as part of REACH’s internal MFS guidance.

In general, and in line with MFS guidance, the best outcome should receive the maximum score, the worst should receive a score of 0, and intermediate thresholds along the way should receive scores between the minimum and maximum (except in the case of yes/no questions and other binary variables). The cumulative score for each dimension is then weighted based on the table below.

Weighting the Dimensions

Although all five dimensions of market functionality are relevant to markets worldwide, they have varying weights within the MFS to reflect their assumed relative importance and interdependence. For example, because a market’s most basic function is to make goods available to local populations, the core availability of these goods is among the most heavily weighted dimensions of the MFS.

On the other hand, the affordability of goods is often tightly linked to their availability, as shortages and unstable supplies are one of the major drivers of price rises in most contexts; as a result, affordability receives a lower weight to avoid having a single underlying dynamic (absence of core goods) dominate the MFS via multiple dimensions.

Table 1: MFS Dimension Weights

| MFS Dimension | Suggested Weighting |
| --- | --- |
| Accessibility | 25/100 |
| Availability | 30/100 |
| Affordability | 15/100 |
| Resilience | 20/100 |
| Infrastructure | 10/100 |

The table above shows the weights that have been assigned to each dimension of the MFS, which represent the maximum score that each of these dimensions can receive. These weights are standard across countries to enable cross-crisis comparison of MFS values.

Calculating the MFS Score

Overall, the MFS is calculated out of a total maximum score of 100, which would reflect a market with no concerns whatsoever about accessibility, availability, affordability, resilience, or infrastructure. The following classification framework is used to assess whether a market has full, limited or functionality, severe issues, or that there is insufficient data to calculate a full MFS.

| Functionality | Threshold/Criteria |
| --- | --- |
| Full Functionality | (1) total MFS is > 80% of the maximum total score and (2) no dimension falls beneath 50% of its maximum score |
| Limited Functionality | (1) total MFS is > 70% of the maximum total score or (2) no more than one dimension falls beneath 50% of its maximum score |
| Poor Functionality | (1) total MFS is < 50% of the maximum total score or (2) at least two dimensions fall beneath 50% of their maximum scores |
| Severe Issues | (1) total MFS is < 25% of the maximum total score or (2) at least three dimensions fall beneath 50% of their maximum scores |
| Insufficient Data | One or more entire dimensions could not be collected in this market, making it impossible to calculate a full MFS |

  - Limitations, Potential Challenges and Mitigation Measures

The methodology adopted for the JMMI offers valuable insights into market dynamics and functionality. However, the following limitations should be considered when interpreting the findings:

Temporal Limitations: The price data is only indicative for the time frame within which it was collected. Prices may vary between data collection rounds due to a variety of external factors, such as changes in supply, demand, or market shocks. This temporal variability requires cautious interpretation of data trends. It also highlights the importance of regular data collection to capture evolving market dynamics.

Variations in Product Types: The JMMI data collection tool requests the cheapest available type of each item to be recorded, as availability varies across regions. Consequently, price comparisons across regions may be based on slightly varying products. While this approach enables the inclusion of diverse products available in different markets, it may lead to potential discrepancies in product quality and type across regions.

Measurement Challenges: In Sudan, standardising unit sizes of some food items could be difficult, as many traders sell commodities by volume rather than weight. This could potentially lead to measurement errors, affecting the accuracy of price data and complicating comparisons across different markets and timeframes.

Coverage Bias: Predominantly, data is collected from main markets, which may not be fully representative of rural areas where market dynamics can differ significantly. This urban bias may limit the scope of understanding market conditions and potentially exclude crucial insights from more remote, underserved communities.

Shifts in Coverage: As the JMMI continues to expand and adapt to additional locations, reported changes in overall median prices may be driven more by shifts in coverage rather than actual price changes. This reflects the challenges in disentangling the effects of evolving data collection operations from genuine market fluctuations.

To address these limitations, several measures could be considered:

Regular and Consistent Data Collection: Regular data collection rounds could help capture evolving market dynamics and mitigate temporal limitations.

Product Harmonisation: Where possible, efforts could be made to harmonise the types and qualities of products being compared to reduce potential discrepancies.

Inclusion of Rural Markets: To address coverage bias, consideration could be given to incorporating more rural markets within the data collection process. This is contingent, however, upon partner capacity to collect data in rural markets.

Tracking Coverage Changes: Careful tracking and transparent reporting of changes in coverage can help in the interpretation of trends, distinguishing genuine price changes from shifts in coverage.

# Key ethical considerations and related risks

The proposed research design meets / does not meet the following criteria:

| The proposed research design… | Yes/ No | Details if no (including mitigation) |
| --- | --- | --- |
| … Has it been coordinated with relevant stakeholders to avoid unnecessary duplication of data collection efforts? | Yes |  |
| … Respects respondents, their rights and dignity (specifically by: seeking informed consent, designing the length of the survey/ discussion while being considerate of participants’ time, ensuring accurate reporting of information provided)? | Yes |  |
| … Does not expose data collectors to any risks as a direct result of participation in data collection? | No | Considering the current uncertain security situation in Sudan, we will need to prioritise safety by reducing unnecessary travel. We plan to ask partners to hire enumerators who are already residing in the localities where data collection will take place. This approach minimises travel risks while also allowing for reliable data collection. We will advise our partners to adopt a similar strategy to ensure both safety and effectiveness of operations. |
| … Does not expose respondents / their communities to any risks as a direct result of participation in data collection? | No | To minimise potential risks to respondents and their communities during data collection, and given the current security situation, extra emphasis will be placed on training enumerators. In line with standard protocol, when conducting surveys, participants will be adequately informed about the purpose of the survey, their right to refuse participation at any point, and reassured that their personal information will not be disclosed to unauthorised parties, thus fostering a secure and trusting environment. |
| … Does not involve collecting information on specific topics which may be stressful and/or re-traumatising for research participants (both respondents and data collectors)? | Yes |  |
| … Does not involve data collection with minors i.e. anyone less than 18 years old? | Yes |  |
| … Does not involve data collection with other vulnerable groups e.g. persons with disabilities, victims/ survivors of protection incidents, etc.? | Yes |  |
| … Follows IMPACT SOPs for management of personally identifiable information? | Yes |  |

# 5. Roles and responsibilities

Table 3: Description of roles and responsibilities

| Task Description | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research design | REACH Assessment Officer (AO) | REACH Research Manager (RM) | JMMI Taskforce, IMPACT HQ Research Design and Data (RDD) Unit | JMMI Taskforce, CWG |
| External engagement | RM | RM | DCC CC | JMMI Taskforce CWG |
| Data collection tools | AO | RM | JMMI Taskforce, IMPACT HQ RDD Unit | CWG |
| Training of partners | REACH Senior Field Officer (SFO), AO | RM | JMMI Taskforce | JMMI Taskforce CWG |
| Coordination of Coverage | SFO, AO | RM | RM | DCC |
| Supervising data collection | SFO, AO | RM | RM | DCC |
| Data processing (checking, cleaning) | AO, FO, REACH Data Officer (DO) | RM | JMMI Taskforce, IMPACT HQ RDD Unit, SAO | REACH DCC |
| Data analysis | DO | RM | IMPACT HQ RDD Unit, REACH SAO | JMMI Taskforce, REACH CC |
| Output production | AO (for the Dataset & Factsheet) REACH GIS (for maps) | RM | REACH CC, IMPACT HQ Research Reporting (RR) unit | JMMI Taskforce |
| Dissemination | RM | RM | JMMI Taskforce, REACH CC, REACH Comms & Advocacy Unit | REACH CC |
| Monitoring & Evaluation | AO | RM | JMMI Taskforce, REACH CC, REACH MEL Unit | IMPACT HQ RDD Unit |
| Lessons learned | SFO, AO, DO, JMMI Taskforce | RM | JMMI Taskforce, CC, REACH MEL Unit | IMPACT HQ RDD Unit |

Responsible: the person(s) who executes the task

Accountable: the person who validates the completion of the task and is accountable of the final output or milestone

Consulted: the person(s) who must be consulted when the task is implemented

Informed: the person(s) who need to be informed when the task is completed

# 6. Data Analysis Plan (DAP)

| Research questions | IN # | DC Method | Indicator / Variable | Question | Type | Responses | DC Level | Sampling | Aggregation / Disaggregation | Aggregation / Disaggregation - First indicator / variable | Aggregation / Disaggregation - Second indicator / variable | Aggregation / Disaggregation - Third indicator / variable | Weighting? | Adjust for design effect? | Significance Test? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MD.1 | KII | Date of data collection | Date of data collection | date |  | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.2 | KII | Name of data collection partner | Name of partner organization | select_one | [list of partners] | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.3 | KII | Enumerator ID | Enumerator ID | select_one | [list of enumerators IDs per partner] | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.4 | KII | Type of data collection | Type of data collection | select_one | Face-to-face Remote | KI | Purposive | NA |  |  |  |  | No |  |
|  | MD.5 | KII | Name of state | Name of state | select_one | [list of regions] | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.6 | KII | Name of district | Name of district | select_one | [list of districts] | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.7 | KII | Name of marketplace | Name of marketplace | text | Free text | KI | Purposive | NA |  |  |  |  |  |  |
|  | MD.8 | KII | Type of vendor | Type of vendor | select_multiple | General store for food and NFIs Specialised store Permanent market stall Open-air vendor Other (please specify) | KI | Purposive | Aggregation | District | State |  |  | No |  |
|  | MD.9 | KII | Consent script | Hello, my name is _ _ _ _. I am working on behalf of [organization] and the Sudan Cash Working Group. I am conducting interviews with traders to better understand how markets in your area are currently functioning. I would like to ask you some questions about the prices and supplies of certain items you sell. Any information you provide will not be used to identify you. Responses are voluntary and you can choose to stop the interview, not answer questions, or ask questions of your own at any time. However, we hope you will participate since your views are important. The survey will take approximately 30 minutes to complete. Do you agree to start the interview? | select_one | Yes No | KI | Purposive | NA |  |  |  |  | No |  |
|  | MD.10 | KII | Gender of trader | Gender of the trader | select_one | Male Female | KI | Purposive | Aggregation | District | NA | NA |  | No |  |
|  | OP.1 | KII | Market open days | How many days a week is this market open? | integer | Integer | KI | Purposive | Aggregation | District | NA | NA |  | No |  |
|  | OP.2 | KII | # of customers | How would you describe the number of customer in the marketplace compared to last month? | integer | Integer | KI | Purposive | Aggregation | District | NA | NA |  | No |  |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.1 | KII | MEB items sold by assessed vendors | Which of the following food items do you usually sell, if any? | select_multiple | [list of all food items in the list + "This trader does not sell any of the listed items (sold none)"] | KI | Purposive | NA |  |  |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.2 | KII | MEB items sold by assessed vendors | Which of the following household items do you usually sell, if any? | select_multiple | [list of all household items in the list + "This trader does not sell any of the listed items (sold none)"] | KI | Purposive | NA |  |  |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.3 | KII | MEB items sold by assessed vendors | Which of the following hygiene items do you usually sell, if any? | select_multiple | [list of all hygiene items in the list + "This trader does not sell any of the listed items (sold none)"] | KI | Purposive | NA |  |  |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.4 | KII | Availability of core MEB monitored items in the assessed marketplaces | How would you describe the current availability of each of the following food items in this marketplace? - Sorghum - Onions - Ful Masri - Vegetable oil - Milk (fresh) - Cow meat (fresh) - Goat meat (fresh) - Dried tomato - Sugar - None | select_one | For each item in the list: Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.5 | KII | Availability of core MEB monitored items in the assessed marketplaces | How would you describe the current availability of each of the following household items in this marketplace? - Gas cylinder - Gas refill - Water container - Water refill - None | select_one | For each item in the list: Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | AV.6 | KII | Availability of core MEB monitored items in the assessed marketplaces | How would you describe the current availability of each of the following hygiene items in this marketplace? - Body soap - Toothpaste - Tooth brushes - Laundry soap - Liquid dish soap - Sanitary pad - None | select_one | For each item in the list: Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | PR.1 | KII |  | To be asked separately about each monitored item: Do you sell [this item] in units of [standard unit]? | select_one | Yes No | KI | Purposive | NA |  |  |  |  | No | No |
|  | PR.2 | KII |  | To be asked separately about each monitored item where relevant: If not, what is the standard unit you use to sell [this item]? | integer |  | KI | Purposive | NA |  |  |  |  | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | PR.3 | KII |  | To be asked separately about each monitored item: What is the current price *received in cash*, of the above unit of (the cheapest type of this item) in Sudanese pounds? | integer |  | KI | Purposive | Aggregation | District | State |  | Median-of-medians | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | PR.4 | KII |  | To be asked separately about each monitored item: What is the current price *received through bankak*, of the above unit of (the cheapest type of this item) in Sudanese pounds? | integer |  | KI | Purposive | Aggregation | District | State |  | Median-of-medians | No | No |
| What are the prices and availability of basic food and non-food items in the markets, and how do these vary over time? | PR.5 | KII |  | To be asked separately about each monitored item: For how many days, not including today, do you estimate your stock of [this item] will last under current conditions? Please include stock that you may have in accessible storage elsewhere. | integer |  | KI | Purposive | Aggregation | District | State |  | Median-of-medians | No | No |
|  | PR.6 | KII |  | To be asked separately about each monitored item: How many days, not including today, would it take you to fully restock [this item] if you were to place an order with your supplier today? | integer |  | KI | Purposive | Aggregation | District | State |  | Median-of-medians | No | No |
| Do supply chains for core items market function reliably? | SC.1 | KII | % of interviewed vendors who maintain relationships with multiple suppliers per category of goods assessed | Does your business mostly rely on a single supplier for food items? |  | Yes No Don't know Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.2 | KII | Path of supply chains leading to this market | Is your main supplier of food items located in this district? | select_one | Yes No Don't know Other (please specify) Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.3 | KII | Path of supply chains leading to this market | If so, where does your main supplier of food items get the majority of their goods from? | select_one | - From within Sudan - From another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.4 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan Admin 1 divisions] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.5 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan Admin 2 divisions] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.6 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.7 | KII | Path of supply chains leading to this market | If not, where is your main supplier of food items located? | select_one | - In Sudan - In another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.8 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan states] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.9 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan districts] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.10 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.11 | KII | % of interviewed vendors who maintain relationships with multiple suppliers per category of goods assessed | Does your business mostly rely on a single supplier for household items? |  | Yes No Don't know Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.12 | KII | Path of supply chains leading to this market | Is your main supplier of household items located in this District? | select_one | Yes No Don't know Other (please specify) Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.13 | KII | Path of supply chains leading to this market | If so, where does your main supplier of household items get the majority of their goods from? | select_one | - From within Sudan - From another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.14 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan states] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.15 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan districts] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.16 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.17 | KII | Path of supply chains leading to this market | If not, where is your main supplier of household items located? | select_one | - In Sudan - In another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.18 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan states] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.19 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan districts] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.20 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
|  | SC.21 | KII | % of interviewed vendors who maintain relationships with multiple suppliers per category of goods assessed | Does your business mostly rely on a single supplier for hygiene items? |  | Yes No Don't know Prefer not to answer | KI | Purposive | NA |  |  |  |  |  |  |
|  | SC.22 | KII | Path of supply chains leading to this market | Is your main supplier of hygiene items located in this District? | select_one | Yes No Don't know Other (please specify) Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do supply chains for core items market function reliably? | SC.23 | KII | Path of supply chains leading to this market | If so, where does your main supplier of hygiene items get the majority of their goods from? | select_one | - From within Sudan - From another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do supply chains for core items market function reliably? | SC.24 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan states] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.25 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan districts] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.26 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.27 | KII | Path of supply chains leading to this market | If not, where is your main supplier of hygiene items located? | select_one | - In Sudan - In another country - Don’t know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do supply chains for core items market function reliably? | SC.28 | KII | Path of supply chains leading to this market | State | select_one | [list of Sudan states] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.29 | KII | Path of supply chains leading to this market | District | select_one | [list of Sudan districts] | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.30 | KII | Path of supply chains leading to this market | Country | select_one | - Central African Republic - Chad - Egypt - Eritrea - Ethiopia - Libya - South Sudan - Other (please specify) - Don't know - Prefer not to answer | KI | Purposive | NA |  |  |  |  | No | No |
| Do supply chains for core items market function reliably? | SC.31 | KII | % of interviewed vendors unable to meet customer demand | Over the last month, have you had any difficulty obtaining enough of any items you sell to meet your customers' demand? | select_one | Yes No Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do supply chains for core items market function reliably? | SC.32 | KII | Supply chain dysfunction | Which items have been most difficult to obtain? | select_multiple | [list of all monitored items + "Other (please specify)"] | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do supply chains for core items market function reliably? | SC.33 | KII | Supply chain dysfunction | Why have these items been particularly difficult to obtain? | select_multiple | I do not have enough money to purchase these items in the amounts I need My supplier will no longer give me credit to purchase these items in the amounts I need Producers have been producing less of these items Demand for these items has increased The suppliers I usually deal with have been unable to meet my customers' demand Domestic transport restrictions have cut off supply routes for these commodities International border closures have cut off supply routes for these commodities There is a shortage of carriers who can transport the goods I need Other (please specify) Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | SC.34 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| What is the exchange rate of 1 USD into local currency? | ER.1 | KII | Exchange rate | What is the buy rate for 1 USD in SDG? | integer |  |  | Purposive | Aggregation | District | State |  |  |  |  |
| What is the exchange rate of 1 USD into local currency? | ER.2 | KII | Exchange rate | What is the sell rate for 1 USD in SDG? | integer |  |  | Purposive | Aggregation | District | State |  |  |  |  |
| Do all market actors, including customers, have physical/social/ access to markets? | MF.1 | KII | % of interviewed vendors reporting that some customers have faced physical barriers to accessing marketplaces over the last month | Over the last month, have there been problems that prevented any customers or traders from physically travelling to, working at, or shopping at this marketplace? | select_multiple | No issues with physical access to the marketplace - Curfew or movement restrictions - Ongoing conflict in the area - Inadequate facilities make it difficult for businesses to operate - Hazardous, damaged, or unsafe buildings in the marketplace Hazards or damage on roads leading to the marketplace - Limited transportation options / lack of transportation - Retailers are difficult to access for people with disabilities or mobility issues - Marketplace only operates at Limited times - Customers do not feel safe around some people in the marketplace - Other (please specify) - Prefer not to answer - Don’t know | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.2 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| Do all market actors, including customers, have physical/social/ access to markets? | MF.3 | KII | Presence of interviewed vendors reporting that some customers have faced social barriers to accessing marketplaces over the last month | Over the last month, have there been any groups of people that sometimes avoided coming to this marketplace due to discrimination, exclusion, or feeling unwelcome? | select_one | Yes No Don't know Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do all market actors, including customers, have physical/social/ access to markets? | MF.4 | KII | Presence of interviewed vendors reporting that some customers have faced social barriers to accessing marketplaces over the last month | Which specific groups are affected and in what ways? | text | Free text | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Do all market actors, including customers, have physical/social/ access to markets? | MF.5 | KII | % of interviewed vendors reporting concerns about lack of safety and/or insecurity in their marketplaces over the last month | Over the last month, have any of the following security factors had a negative impact on your business, your customers, or you personally while doing your work? (Select all that apply) | select_multiple | No issues with security in or near the marketplace - Curfew or movement restrictions. - Fear of insecurities - Fear of discrimination - Fear of physical harassment or violence - Fear of sexual abuse, exploitation or harassment -[Sexual exploitation is abuse of a position of vulnerability, differential power or trust for sexual purposes It includes sex for something e.g profiting monetarily, socially or even politically from the sexual exploitation of another] - Fear of arbitrary detention - Fear of criminality - Fear of being injured/killed by an explosive hazard/mines/UXOs - Other (please specify) - Prefer not to answer - Don't know | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.6 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| Do all market actors, including customers, have physical/social/ access to markets? | MF.7 | KII | % of interviewed vendors reporting that some customers have faced financial barriers to accessing marketplaces over the last month | Do customers of your business face any financial challenges in travelling to you or in paying for the goods they need? | select_multiple | Most customers have no issues with financial access - Many customers cannot afford the items available - Many customers cannot pay for their items in a way you can accept (f. ex. not enough cash, No mobile money account, etc.) - Many customers do not have access to physical cash (low availability of paper bills) - Many customers do not come due to their inabiity to pay for outstanding purchases on credit. - Public transportation is too expensive for Many Customers - Fuel is too expensive for many customers - Other (please specify) - Prefer not to answer - Don’t know | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.8 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| Are the prices for core items stable in this market? | MF.9 | KII | % of interviewed vendors unable to predict price changes over the next month | Think of the most popular items you sell. If we were to ask you what prices your suppliers will charge you for those items one month from now, do you think you would get it right? | select_one | - Yes - No - Don't know - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
| Can vendors in this market reliably provide all core items that local households need to purchase on a regular basis? | MF.10 | KII | % of interviewed vendors reporting difficulties keeping their business operational and well-stocked over the last month | What are, if any, the difficulties you are currently facing to keep your business operational and well-stocked? | select_multiple | No difficulties Difficulties with availability of core goods Difficulties with prices charged by suppliers Difficulties accessing money and/or cash to pay suppliers Difficulties accessing physical cash (low availability of paper bills) to pay suppliers/owner of rental Difficulties fully staffing your store Difficulties related to movement restrictions Difficulties related to physically dangerous conditions in this area Difficulties with unstable electricity and power cuts Difficulties with high rental prices Other (please specify) Prefer not to answer Don’t know | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.11 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| Do vendors have access to locked, secure storage facilities where they can keep their stock? | MF.12 | KII | % of interviewed vendors reporting that they lacked access to a locked, secure storage facility for their stock within their marketplaces over the last month | Over the last month, have you had access to a locked, secure storage facility within your business facility or marketplace? | select_one | Yes, within my own business facilities Yes, somewhere else within the marketplace No, I store goods at another facility outside this marketplace No, I store goods at my home I do not store goods / I don't have storage Other (please specify) Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.13 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
| Do customers have financial access to markets? | MF.14 | KII | % of interviewed vendors reporting that they accepted payment modalities other than cash or informal credit over the last month | Over the last month, which of the following types of payment have you accepted from your customers? | select_multiple | Cash (Sudanese pounds) - Cash (foreign currencies) - Mobile app payment (bankak, kashi, banki) - Mobile money (MTN, Sudani, Zain) - Credit/debit cards - Money or bank transfers - Hawala - Cheques - Vouchers - Informal Credit (Customers can buy now and pay later) - Barter (Customers can pay for goods with Other goods) - Other (please specify) - Prefer not to answer | KI | Purposive | Aggregation | District | State |  |  |  |  |
|  | MF.15 | KII |  | Please specify: | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
|  | MD.16 | KII | Further context | Do you have any further comments about your business or your marketplace that you would like to share? | text | Free text | KI | Purposive |  |  |  |  |  |  |  |
|  | MD.17 | KII | Further context | [To enumerator] Do you have any observations about this business or this marketplace that you would like to share? | text | Free text | KI | Purposive |  |  |  |  |  |  |  |

# 7. Monitoring & Evaluation Plan

| IMPACT Objective | External M&E Indicator | Internal M&E Indicator | Focal point | Tool | Will indicator be tracked? |
| --- | --- | --- | --- | --- | --- |
| Humanitarian stakeholders are accessing IMPACT products | Number of humanitarian organisations accessing IMPACT services/products Number of individuals accessing IMPACT services/products | # of downloads of x product from Resource Centre | Country request to HQ | User_log | X Yes |
|  |  | # of downloads of x product from Relief Web | Country request to HQ |  | X Yes |
|  |  | # of downloads of x product from Country level platforms | Country team |  | □ Yes |
|  |  | # of page clicks on x product from REACH global newsletter | Country request to HQ |  | X Yes |
|  |  | # of page clicks on x product from country newsletter, sendingBlue, bit.ly | Country team |  | X Yes |
|  |  | # of visits to x webmap/x dashboard | Country request to HQ |  | □ Yes |
| IMPACT activities contribute to better program implementation and coordination of the humanitarian response | Number of humanitarian organisations utilizing IMPACT services/products | # references in HPC documents (HNO, SRP, Flash appeals, Cluster/sector strategies) | Country team | Reference_log |  |
|  |  | # references in single agency documents |  |  | CWG strategy |
| Humanitarian stakeholders are using IMPACT products | Humanitarian actors use IMPACT evidence/products as a basis for decision making, aid planning and delivery Number of humanitarian documents (HNO, HRP, cluster/agency strategic plans, etc.) directly informed by IMPACT products | Perceived relevance of IMPACT country-programs | Country team | Usage_Feedback and Usage_Survey template | Usage survey to be sent out to 10 targeted partners after two months of data collection |
|  |  | Perceived usefulness and influence of IMPACT outputs |  |  |  |
|  |  | Recommendations to strengthen IMPACT programs |  |  |  |
|  |  | Perceived capacity of IMPACT staff |  |  |  |
|  |  | Perceived quality of outputs/programs |  |  |  |
|  |  | Recommendations to strengthen IMPACT programs |  |  |  |
| Humanitarian stakeholders are engaged in IMPACT programs throughout the research cycle | Number and/or percentage of humanitarian organizations directly contributing to IMPACT programs (providing resources, participating to presentations, etc.) | # of organisations providing resources (i.e.staff, vehicles, meeting space, budget, etc.) for activity implementation | Country team | Engagement_log | X Yes |
|  |  | # of organisations/clusters inputting in research design and joint analysis |  |  | X Yes |
|  |  | # of organisations/clusters attending briefings on findings; |  |  | X Yes |

Whilst food prices of commodities included in the Sudan MEB are monitored systematically on a regular basis, this is not the case for NFI items.

Further guidance on how the MFS is calculated can be found in the Methodology section (Data Processing & Analysis)

Indicative insights into financial access for customers will be ascertained from the perspective of vendors, through questions on whether their customers face any financial challenges in travelling to marketplaces or in paying for the goods they need.

The full extent of vendors in each district is unknown. In the JMMI, the sampling pool is not the population but the vendors themselves. Even though the population of vendors is unknown, indicative comparisons can still be made among strata.

DTM Sudan - Situation Report | Displacement Tracking Matrix

WFP report, November 2025

IPC country analysis details

Relief web report Sudan 23 March 2025

The state-level median will be calculated as the median of all district-level medians across the respective state.