| Research Terms of Reference Third Party Monitoring – HMG Strengthen the framework of HMG project interventions inside Syria through the provision of output and outcome monitoring, SYRIA |  |
| --- | --- |
| [Release date] [V.1.2] |  |

# 1. Summary

| Country of intervention | Syria |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Emergency |  | Natural disaster | x | Conflict |  |  | Emergency |  |
| Type of Crisis |  | Sudden onset |  | Slow onset |  | x | Protracted |  |
| Mandating Body/ Agency | UK HMG (FCO, DFID, MoD) |  |  |  |  |  |  |
| Project Code | 16 AiBR 02D |  |  |  |  |  |  |
| Research Timeframe | June 2016 – April 2019 (33,5 months including 2 months inception phase) |  |  |  |  |  |  |
| General Objective | Design and implementation of an output and outcome monitoring framework for HMG and partners operating HMG funded programmes in Syria. Provide updated information on progress and implementation to HMG and their implementing partners on the delivery of the programmes they are undertaking in targeted locations inside Syria, as well as to verify the implementation of the activities as planned. |  |  |  |  |  |  |
| Specific Objective(s) | Development and roll out of outcome and output monitoring tools and visits aligned with HMG strategy and programmes and relevant to the Syrian context; HMG Programmes benefit from a regular independent output and outcome monitoring process . |  |  |  |  |  |  |
| Research Questions | Research questions will be designed based on each of the programs that will be monitored. |  |  |  |  |  |  |
| Research Type |  | Quantitative | x | Qualitative |  | X | Mixed methods |
| Geographic Coverage | Aleppo, Idleb, Rural Damascus, Dara’a, Quneitra. |  |  |  |  |  |  |
| Target Population(s) | N/A |  |  |  |  |  |  |
| Data Sources | Secondary Data: Program documents from each of the programs monitored Internal Monitoring Data from the programs Contextual information about the areas of operation in Syria Primary Data: |  |  |  |  |  |  |
|  | Key Informants interview; Focus Group Discussions, Individual interviews |  |  |  |  |  |  |
| Expected Outputs | Output reporting at the end of each monitoring wave, Bi-annual reports for outcome monitoring Final report Mapping as agreed upon in discussion with HMG Biannual progress report and presentation to the Syria CSSF Board |  |  |  |  |  |  |
| Key Resources | 1 Assessment Officer, 1 Regional Assessment Manager, 1 DB /GIS officer, 1 Field Assistant, 2 Field Coordinators. |  |  |  |  |  |  |
| Humanitarian milestones |  |  |  |  |  |  |  |
|  | Milestone |  |  |  | Timeframe |  |  |
|  |  | Cluster plan/strategy |  |  | Specify which, when |  |  |
|  |  | Inter-cluster plan/strategy |  |  |  |  |  |
|  | X | Donor plan/strategy |  |  | 2016 - 2019 |  |  |
|  |  | NGO plan/strategy |  |  |  |  |  |
|  |  | Other |  |  |  |  |  |
| Audience |  |  |  |  |  |  |  |
|  | Audience type |  |  |  | Specific actors |  |  |
|  |  | Operational |  |  | Specify here. |  |  |
|  | X | Programmatic |  |  | HMG stakeholders |  |  |
|  |  | Strategic |  |  |  |  |  |
|  |  | Other |  |  |  |  |  |
| Access |  | Public (available on research center and other humanitarian platforms) |  |  |  |  |  |
|  | X | Restricted (bilateral dissemination only upon agreed dissemination list, no publication on Ressource or other platforms) |  |  |  |  |  |
|  |  | Other (please specify) |  |  |  |  |  |
| Visibility | HMG and IMPACT logos will be included in all official shared documents. Templates for reporting will be designed as part of the inception phase, shared and approved by HMG. Reports will only be shared with HMG and Partners as agreed in communication plans and following the confidenciality agreement signed between the parties. |  |  |  |  |  |  |
| Dissemination | Findings of this research will be agreed with HMG on a bilateral bases. HMG will be in charge in sharing the results of the research with partners. For outcome monitoring, partners will have the opportunity to feedback into the results once the draft report is finalized. Bi annual high level meetings with HMG members are expected to take place. |  |  |  |  |  |  |

# 2. Background & Rationale

The situation in Syria has significantly deteriorated in 2015 and it is estimated that approximately 250,000 people have been killed since the beginning of the conflict and 6,5 million are internally displaced. An estimated 13.5 million people are now in need of humanitarian assistance and protection, including 4.49 million in hard to reach areas, and some 360,000 in besieged areas. A significant proportion of those in need are children, now estimated at 6 million (2016 Humanitarian Needs Overview). According to UNICEF, 8.7 million people are unable to meet their basic food needs, and 70% of the population lack access to safe drinking water. Community vulnerability has worsened as many essential services, such as health facilities and schools have been closed or are operating at reduced capacity.

The alarming situation in Aleppo city, as well as the intensification of the conflict in other areas in other regions further impede on access and predictability. This high risk security situation makes it extremely challenging for Her Majesty’s Government (HMG) - including the Foreign and Commonwealth Office (HMG), the Department for International Development (HMG) and the Ministry of Defence (MoD), to effectively monitor the delivery and outcomes of HMG programmes in Syria. Many implementing partners also work with downstream partners and have to largely manage these partners and staff implementing the projects inside Syria remotely. As the project locations are inaccessible due to insecurity, HMG relies predominantly on partner reporting, structured meetings with partners and assessment of their M&E systems in order to track progress.

It is expected that the development and inclusion of a systematic third party monitoring in support of HMG-funded programmes will contribute to increase the accountability and effectiveness of such programmes, by providing a regular, predictable, evidence-based and independent information and support HMG implementing partner agencies in assessing their overall performance. In this context, HMG decided to finance this third party monitoring programme.

# 3. Research Objectives

- Overall Objective:

  - To inform HMG CSSF programs through qualitative research in Syria.

- Specific Objectives:

  - Design and implementation of an output and outcome monitoring framework for HMG and partners operating CSSF funded programmes in Syria.

# 4. Research Questions

Research questions have been designed for each of the programs that will be monitored. However, overall this research cycle is looking to answer the following questions:

- Output monitoring: will look into checking if the items anticipated in the program have been purchased, the staff planned for the activities has been hired, and activities planned implemented as intended. This will be specific to each of the programs monitored, as not all of them will have output monitoring as part of the research cycle.

- Outcome monitoring: will look into the achievement of specific outcome indicators designed into the Theory of Change of each of the programs.

- A list of indicators will be added as Annex to the ToRs for each FCO program that will be monitored.

Research questions per program:

- Tamkeen; Implementing Partner: Adam Smith International (ASI)

#### The monitoring is based on following research questions (RQ) that were designed by the donor and reviewed/approved by both the implementing and the monitoring parties:

- Is capacity being built in the Local Council Administrations (LCAs) where the handover is being done, and how? Is there evidence of improved capacity in the planning and management of services/projects?  What are the obstacles to building capacity?

- How are the handover LCAs consulting the community and civil society? Does this consultation have an effect on the projects? What role are women and minorities playing?

- What role is the Tamkeen Committee playing in the community post transition? What role do communities think the Tamkeen Committee should play (in future)?

- Aman Network Program; Implementing Partner Peacebuilding Initiative - CCSD

The Aman Network (AN) contributes towards promoting human security at all levels, as well as building peace capital, contributing to national conversations on the future of Syria, promoting civilian space and stabilisation.

#### The program will be monitored mostly at the outcome level, with some limited output monitoring. The monitoring is based on following research questions (RQ) that were designed by the donor and reviewed/approved by both the implementing and the monitoring parties:

- Has greater reliance on inclusive dialogue-based approach been build? Has cooperation among key local stakeholders and 'across divides' increased? Do Syrians living in the target areas feel more resilient (safer), as they are better able to function in the conflict context?

- Has the AN's capacity to deliver high-impact human security, social awareness, and civil peace interventions increased?

- Have relationships been strengthened between AN and a diverse range of partners to enhance programme impact?

- Has the acceptance of civilian-led initiatives that promote peace and/or dialogue with other sides increased in the target areas?

- Taallum Program; Implementing Partner: Adam Smith International (ASI)

The program will be monitored mostly at the outcome level, with some limited output monitoring. The monitoring is based on the following research questions (RQ) that were designed by the donor and reviewed/approved by both the implementing and the monitoring parties:

- What difference is Taallum making to the capacity of EAs and PEDs to prioritize and deliver education services? What works and why? Have counterparts been able to effectively complete modules? Why/why not? What have they learnt? How have they been able to apply this? Why/why not? What is making the biggest different to the capacity of EAs and PEDs, and their ability to deliver education services? What is preventing them from doing their work, including internal and external factors? Has the AN's capacity to deliver high-impact human security, social awareness, and civil peace interventions increased?

- What difference is Taallum making to conditions for teaching and learning in pilot locations (including in the classrooms)? How have conditions for teaching and learning changed? Why? Why not? What has caused these changes? What are the barriers for parents in sending their children to school? How have these changed? Why? Why not? What has caused these changes?

- Stabilization Response Mechanism (SRM); Implementing Partner: Adam Smith International (ASI)

Due to the particular structure of the SRM program, research questions cannot be established as a whole for the entire SRM program but are established on a rolling basis once projects are identified.

The desired impact of the SRM project is that: Syrians are reassured that there are credible moderate alternatives to extremism and the Assad Regime. In order to ensure maximum flexibility, the methods by which this impact is achieved are not prescribed, but outcomes include:

- Rapid, prioritised and equitable delivery of services supported

- Capacity of Syrian governance institutions and civil society organisations to deliver services increased

- Effective, coordinated and coherent donor response enabled

- Tension reduced and trust built between, and within, communities

In support of this flexible approach, IMPACT has designed a flexible monitoring protocol that ensures appropriate monitoring response, as soon as a project is identified.

# 5. Methodology

  - Methodology overview

These ToRs contain the overall methodology framework proposed to FCO in the proposal, as well as the specific methodology design for each of the programs that will be monitored. The overall steps followed in the methodology are:

- Introduction to the partners and the programs, for a good understanding of the objectives, results, and research questions.

- Selection of outputs and outcomes that will be monitored in each program.

- Design of the indicators, means of verification, and data collection methods.

- Design, and piloting of the tools.

- Selection of final locations, training, and full roll out data collection.

Overall, the monitoring will be organized according to two types of monitoring: output monitoring and outcome monitoring. The output monitoring aims at identifying and verifying that services and activities funded by HMG and implemented by a HMG partner are being effectively delivered and received as initially planned. The outcome monitoring will be directed to evaluate the outcomes of selected programmes implemented in the specific locations.To perform these two types of monitoring, a combination of different methodologies is required, based on the nature of the specific programme to be monitored, the information to be collected, and indicators to be measured.

In the following monitoring described methodology, it is expected that output monitoring by location will take approximately one day for 2 monitors, whereas outcome monitoring per location will be rather implemented over a 2 to 3 day period including 2 monitors. As much as security and context allow, our teams  will pair one man with one woman in each team to ensure the inclusion of a gender lense to the monitoring. However, the recruitment of women in the context of Syria remains challenging, which means we  may not be in a position to ensure this pairing systematically. This will be discussed with HMG, and, as part of the hiring process, the recruitment of women will be systematically sought. Until now, females have been accordingly identified in each location where they are needed for the implementation of the activities.

  - Population of interest

Overall, this program will be implemented in six governorates during the three years of the program: Aleppo, Idleb, Rural Damascus, Dara’a, and Quneitra. The final locations of monitoring will be decided upon in discussion with HMG and their partners each quarter. The monitoring will be organized at the community level.

Secondary data review

For the purpose of this program, IMPACT will use SDR in order to better understand the scope, scale, objectives, and activities of the programs that will be monitored, as well as a source of information to answer the research questions.

The information selected as SDR will be, among others, project documents produced in the framework of each of the programs; meeting minutes, briefing notes, or documents produced to record meetings; beneficiary lists, supply delivery lists, procurement lists, equipment lists; security reports, from INSO, and other NGOs etc…Other relevant documents will be added in each program as needed.

For programs documents to be considered, they will have to meet the following criteria:

- To have been produced within the life of the program being monitored, or in case of evaluations, within 3 to 6 months of the finalization of the program

- Documents in Arabic will have to be provided with an exact translation in English

- Information will have to be relevant to the program being monitored, as well as original – produced in the framework of the program by the partners or the beneficiaries

  - Primary Data Collection

5.4.1 Overall Methodology

The methods that will be used overall in this research are:

Qualitative methods:

Direct observations (DOs)

The monitors will be trained to use direct observation techniques, which will allow them to record information on what is exactly happening at the monitoring site. Direct observation allows for a more systematic and structure process when using well-designed observation forms. Despite the benefits of direct observation, this method is susceptible to the monitors bias. Combination of this methodology with other qualitative methodologies, as well as a strong training, will minimize this possible bias during the recording of the DOs. Timing is one of the most important aspects in direct observation, as the data collection using this type of method needs to allow for the events or elements that need to be monitored, to be observed.

The focus of the direct observation in each site or monitoring need to be selective and focused on particular aspects that are agreed and central to the monitoring exercise for which the direct observation method is being used.

Key informant interviews (KIIs)

This method is proven to be effective in a context such as Syria, where remote management, lack of accessibility, and a highly volatile and dynamic context impedes probability sampling. In addition, KIIs will be used to collect more quantifiable data as well as to obtain ranking and rating that cannot be obtained through FGDs. IMPACT INITIATIVES will design, in cooperation with HMG, a comprehensive list of key informants per each project and activities that will be monitored. Key informants will be identified based on their level of knowledge of the particular monitoring activity, location and sector to be undertaken, and shall not be considered systematically as direct beneficiaries of the programme. They consist of people who have a direct knowledge and therefore information to share on the programme, like for instance:

- Beneficiaries: those who benefited directly from the activities implemented, as well as those who were directly impacted by these.

- Individuals that implemented the programs: such as program managers, program officers, key members of specific departments, local councils, etc.

- Other individuals with knowledge of the action, of its outputs and/ or of its outcomes.

Sampling: purposive sampling of these key informants will be applied based on the expertise of the key informants and the accessibility in each monitoring location. The objective of this type of sampling will be also to obtain information about the effect that the programme has in different key groups that may be affected – or not affected – directly.

The key informants will provide information corresponding directly to their area of knowledge, thereby mitigating unfunded deductions. The key informants will be given closed to semi structured interview questionnaires – depending on the monitoring activity and the sector being monitored. These key informant interviews align with one of the main intentions of the monitoring process of this programme.

Focus Group Discussions (FGDs)

Focus group discussions will take place in specific communities where monitored projects are being implemented. The main objective in using this methodology as part of this programme will be to understand different views and perspectives on the monitored projects as well as the way group dynamics affect views on different issues.

The purpose of the FGDs will be to explore particular issues that may have been identified either during the design of the monitoring process, or also by previous KIIs, to explore meanings that cannot be explained statistically, and identify a range of views on a topic of interest, as well as grasping potential views that show to be dominating among the group/community. FGDs will take place with people over 18 years of age, both male and female, mobilised in separate sessions, to ensure gender balance representation. Specific trainings of the enumerators, both on the questionnaire and on the topic, will be implemented within weeks before the implementation of the FGDs to ensure that qualitative and usable information is collected.

Sampling: for FGDs, purposive selection of the participants will be applied, in order to be able to have participants who are the most adequate to answer the questions. Implementing partners will be key in supporting in identifying members of these FGDs.

FGDs selection of locations will be purposively sampled, based on each of the programs and bilateral discussions with each of the program focal point and HMG. Locations will vary depending on access, implementation of the program, point in time in which the monitoring will take place, among others. FGDs will be between 6 and 10 participants.

For each of the FGDs within each project, the participants of the FGDs will be selected based on a screening list. In each program, a specific screener will be drafted to better target the participants. However, the main overarching objective criteria will be:

- Demographics: always over 18 years old.

- Gender: male and female focus group discussions will take place, together or separate, depending on the location and topic.

- Location.

- Knowledge of the program: how long they have been involved.

- Category in which they know the program: beneficiaries, participants, stakeholders, implementers, etc.

Depending on these last two, categories will be developed for the participants to be identified within specific groups that will help the analysis of the information. It is essential that all FGDs avoid including:

- Beneficiaries/participants from similar programs but not the ones being monitored.

- Beneficiaries /participants that are not currently involved in the programs for personal decision.

- Beneficiaries/participants who have never been exposed or involved in the program.

- Biased beneficiaries/participants due to their personal relations, participation on specific armed/religious/social groups.

The number of FGDs per location, and type, will be decided in the framework of each program and in each location. This will be influenced by the number of days available for monitoring per program and per location.

In order to measure data saturation, a saturation grid will be constructed to guide the monitors in the field to check when all the information that is needed for the purpose of the FGD has been collected. This saturation grid will contain on the left the complete list of ideas / topics that need to be discussed, and on the right the number of times/ and if that has been mentioned in the conversation.

The FGD forms will be translated into English and the answers will be coded into categories for its easier analysis into an excel database. This process is outlined in the section Data Analysis below, and specific ToRs for these will be developed. Specific security and safety norms for the implementation of these FGDs will also be implemented, as well as confidentiality rules into the instructions of the questionnaires that the FGDs facilitators will need to carefully consider.

Remote data collection methodologies and Area of Origin Network

Because of the dynamic and multi-faceted nature of the Syria crisis, accessibility and security issues will be a constant challenge in maintaining a systematic direct data collection system, whether quantitative or qualitative. As part of this monitoring project and given some projects to be monitored are implemented in hard to reach / non accessible areas, IMPACT may also rely on remote data collection techniques. The use of this technique in the framework of this program will be decided on a case by case scenario together with HMG and their partners.

5.4.2 Methodology per program

a) Tamkeen Program

b) Aman Network Program

c) Taallum Program

d) SRM Program

The particularities of the SRM program will not allow for the definition of indicators to be measured as a whole for the entire SRM program. Under the SRM mechanism, different projects will be submitted by ASI to FCO to be funded under SRM. TPM will apply to these projects if the comply with one or more of the criteria developed by them and approved by FCO – these criteria are:

a) value greater than 100,000 USD

b) high risk project and/or challenging for SRM to monitor

c) strategic significance to SRM/HMG

At the inception phase, IMPACT will submit to SRM team the template in which we will develop the indicators for each program that has been approved and is ready to be implemented in Syria. The template can be found in Annex 4.

  - Data Analysis Plan

The nature of this research will be mainly qualitative, and will involve a lot information collected through open ended questions and semi structured questions. For this reason, the nature of the data collection system and data analysis plan will require a more structured system, lacking the capacity for undertaking direct mobile data collection directly.

KI – as much as possible, these will be undertaken using mobile data collection.

FGDs – this will be done through qualitative note taking, translation and coding.

A methodology framework, with indicators and type of data collection methods, level of aggregation, and target groups will be designed as part of the inception report of this program. That will constitute the core of the analysis plan per each program.

Preparation for Analysis

After each data collection session, monitors are debriefed by the team leaders in each of the governorates where data collection has taken place. This first debriefing session will consist in reviewing the questionnaire and making sure all fields have been correctly filled in, and all notes for FGDs are comprehensive and clear.

Once this first check has taken place, the Database Officer and the Field Assistant, will proceed to check the information on the forms. They will identify any mismatching or strange information, and read through all of forms to make sure everything is correct and clear. When needed, they will organize debriefing sessions on the phone and Skype with the monitors. Data will be triangulated whenever a suspicion of flawless information, or lack of accuracy arise.

Part of this data check and data cleaning will include back translation in all cases where FGD and open-ended KIIs are implemented are implemented. Once all qualitative information has been translated, sections of the information are back translated into Arabic one more time to make sure the information is accurate. Records of these back translations will be created to make sure the process is documented.

Analysis

Data collected in through close ended questions (both by DO and KIIs) will be in the shape of short yes/no or categorical answers. Still, some coding will be necessary in order to assign number/symbols to answers categories. During this process, the same code will be given to common responses, irrespective of the question (Don’t know = 8; refuse to answer = 9; etc.). Codes will be then compiled into a code book, to ensure the database can be easily read and analyzed.

The database will be then submitted to a descriptive analyses process in order find possible relationships between variables. For this purpose, the analysis will include calculation of frequencies (counts) and percentages of answers for example. Data will be also broken down by the different target groups and other relevant features (gender, profession, institution the person is affiliated to, etc.) in order to better explore possible relationships between variables.

The analysis of data collected in the qualitative text notes (both FGDs and KIIs) will rely on field notes taken by monitors during the interview/discussion, as well as on the monitors’ post-FGD debriefing. All notes of FGDs and KIIs will be manually coded. Notes will be split into sentences then divided according to the key QR and indicators that the research intends to address - when specific answers concern multiple RQ/indicators. At this stage, the analysis started by identifying key issues in each QR/indicators and defining brief summaries accordingly. The analysis will focus on:

- Frequency:  the analysis takes into account how many times issues were reported by FGD and KII participants.  However, as per best practice in qualitative research, frequency has not been associated with higher or lower importance. Frequency will inform the analysis on how much these specific issues are spread amongst the research target groups.

- Specificity: more emphasis will be given to specific, detailed issues that were reported, always taking into account bias of the respondents

- Emotion and behaviours: more weight will be assigned to themes and comments that participants reported that showed enthusiasm, passion or intensity, as well as to the ones that they seem to appear indifferent to.

- Extensiveness: extensiveness of comments will be linked to how many different participants have reported a specific comment or issue.

The following analytical framework will be used during the analysis:

Constant Comparison will be used to identify patterns and discover relationship between ideas and concepts and to understand the different trends and to identify common opinions among TC or LAC members, CSO representatives. In order to do that, that analysis will be processed through three major stages:

- Open Coding: all collected data will be consolidated into small units and a code, or description will be attached to each small unit.

- Axial Coding: small units will be aggregated into categories according to their codes. For instance, a category for “Guidelines and Forms” will be created by associating coding such as “Procurement”, “Budget and Finance”.

- Selective Coding:  one or more thematic will be identified by grouping categories.  For instance the thematic “Process and Protocols” will be identified by associating “Guidelines and Forms” and “MoU Process”

Table 2: Constant Comparison analysis steps

| Steps | Action | Description | Purpose |
| --- | --- | --- | --- |
| S1 | Open Coding | Data is consolidated into small units and labeled with a code | Re-organize large amount of qualitative data |
| S2 | Axial Coding | Small units are aggregated into categories according to their codes | Aggregate the different pieces of data into larger categories |
| S3 | Selective Coding | Themes are identified by groups of categories | Identify larger thematic areas to which the different categories are related to |

This analysis approach will serve as proxy for theoretical sampling. It will help identifying if themes that emerged from a specific groups or individual are relevant to other groups or individuals. This approach also assists analysis to quickly reach data saturation, therefore saving time and resources. For this purpose, the FGD analysis will be done just after each day of data collection to track data saturation. Once enough data is obtained, the FGD’s will be re-oriented in order to collect data that may still missing.

Even though data will be heavily coded for analysis purposes, the report will contain the most significant participants’ statements when possible and relevant. Quoting the verbatim will be used to illustrate the main themes emerged from the analysis as well as to enhance readability of the report.

Key concept analysis will be used to analyse individual interviews. Individual surveys to identify key issues and to better understand specific participants’ perceptions on the TC handover process. After the completion of the constant comparative analysis, the identified categories and summary will be tested against the KIIs findings. Hierarchy of problematic findings will be defined and contradicting comments were addressed.

# Product Typology

The products that will be delivered under the current programme will be:

Table 1: Type and number of products to be delivered

| Type of Product |  | Number of Product(s) in 3 years | Additional information |
| --- | --- | --- | --- |
| Inception report (6 weeks to 2 months after the signature of the contract) | 1 |  | The report will include the revised work plan for the whole contract, final budget, final quarterly/annual payment plan, final key performance indicators and risk matrix, quarterly financial and bi-annual narrative reporting templates, refined methodology for the monitoring visits and the remote monitoring, data management plan as weel as monitoring tools of all output and outcome monitoring. |
| Report after each monitoring wave | 1 per monitoring wave |  | Reports summarising key output monitoring findings. Each implementing partner will have two weeks to correct any factual inaccuracies based on empirical evidence before a final version is finalized and shared. |
| Report for outcome monitoring (bi-annual) | 5 |  | Analytical reports on programmes outcomes. The reports will be verbally presented in meetings to members of the FCO programmes. |
| Final report (bi-annual) | 5 |  | Reports no longer than 10 pages summarizing key findings from the monitoring activities for the previous six months. The reports will be presented verbally to the programmer’s steering group and other stakeholders from the FCO, DFID and the MoD. The reports will include a section on lessons learned that will intend to feed into the second year of the contract. |
| Meetings (bi-annual) | 5 |  | Meetings with DFID and FCO focal points at HQ level on monitoring progress and potential challenges. These meetings will be scheduled based on both IMPACT and DFID key staff availability. |
| Aggregated database with collected data (bi-annual) | 5 |  | Complete database as well as analysis workbooks and visuals will be adequately stored and submitted at the end of each six months work plan. |
| Mapping of the locations of the monitoring and progress. | ns |  | The number of maps, contents and frequency will be discussed with FCO during the inception phase as well as on an ongoing basis, based on the needs of the program. |
| Sources of verification of monitoring activities (bi-annual | ns |  | Various material such as pictures, videos, questionnaires filled in, etc., that will be adequately stored and submitted to FCO on a regular basis, as agreed during the inception phase. |

# 7. Management arrangements and work plan

##### 7.1. Roles and Responsibilities, Organigram

Core IMPACT Initiatives programme team:

IMPACT Syria operations are managed by dedicated international and national staff in Turkey and Jordan. This project will be managed by two hubs, one based in Gaziantep (Turkey) and a second hub based in Amman (Jordan), covering the north and the south areas of Syria respectively:

Northern Syria team

- IMPACT INITIATIVES Assessment Manager, Syria Crisis (expatriate, part time): will oversee the assessment cycle in country, as well as will liaise with HMG and external actors. Will supervise the overall monitoring and validation of surveys, materials, and reports. The Assessment Manager has an assessment, research, and management background, with focus in research in conflict countries in the MENA region.

- IMPACT INITIATIVES Syria Assessment Officer (expatriate, full time): supervised by the Assessment Manager, will coordinate and ensure the implementation of the assessment, including design of the tools, implementation of data collection, cleaning, analysis, and reporting. The Assessment Officer has a qualitiative research background, including monitoring and assessment expertise, with an emphasis in social sciences, and good command of excel and other analytical tools, as well as in information management.

- IMPACT INITIATIVES Database / GIS Officer (national, part time): will support the data collection and data entry process; liaise with the team leaders for debriefing sessions, and collect and organize questionnaires from the field. This position also supports on back translations and language checks. The Database Officer has a technical background in Information Technology, including databases and mapping.

- IMPACT INITIATIVES Field Coordinator (national, part time): supervised by the Assessment Officer, he will support on the liaising with the team leaders, organize the monitoring visit schedules, as well as follow up on the data collection monitoring. The Field Coordinator has a background on monitoring and evaluation as well as engineering and coordination of teams in the field.

- IMPACT INITIATIVES Field Assistant (national, part time): supervised by the Field Coordinator, this position is in charge of all the monitors HR support, master tracker data entry and cleaning, translation of questionnaires and back translation, as well as support to the Field Coordinator. The field assistant has a background on monitoring and evaluation, data collection and data management, HR support to field teams, among others.

- IMPACT INITIATIVES Field Coordinator (national, full time): supervised by the Assessment Officer in Amman, she will support on the liaising with the team leaders, organize the monitoring visit schedules, as well as follow up on the data collection monitoring.

The presence of the team in Amman is part of a current scale up that IMPACT will implement to work in areas of sourthern Syria.

Inside Syria team:

Field Team leaders – 5: supervised by the the IMPACT team in Gaziantep and Amman. Team leaders will coordinate and supervise the data collection process in each of the governorates; the field monitors will be supervised directly at the field level by the field team leaders. The field team leaders in Syria are among the most experienced people withing the team in each governorate.

- Field monitors – to implement the data collection in the selected areas in each of the governorates in Syria. All IMPACT team leaders and monitors benefitted from multiple trainings that covered topics like team structure, roles and responsibilities of the monitors, monitoring types and techniques, the use of KoBoCollect, the code of conduct as well as safety and security in the field. The same training is followed by any new monitor joining the team. In addition, trainings are carried out on a regular basis to  refresh the main concepts of the monitoring process, to review lessons learned and best practices, as well as to learn using new tools and techniques.

Organigram

Responsible: the person(s) who execute the task

Accountable: the person who validate the completion of the task and is accountable of the final output or milestone

Consulted: the person(s) who must be consulted when the task is implemented

Informed: the person(s) who need to be informed when the task is completed

RACI matrix has been included in Annex 11.

  - Resources: HR, Logistic and Financial

This research cycle has a total budget of 833,400 GBP for a total duration of three years. This budget includes all HR and logistical resources to make possible the research as outlined in the proposal and in these ToRs.

Hiring and HR policies

IMPACT monitors team is a long standing team of professional data collectors that are a core part of the IMPACT team in Syria. With more than two years of experience in Syria, they have been trained and working in assessments, research, monitoring and various data collection techniques since 2013. IMPACT’s policy of professional development, as well as quality on duty and responsibility of the work it does in Syria influences the definition of its policies for hiring monitors. Some of these principles are:

- IMPACT Initiatives hires staff with at least a high school degree, and mostly with college degrees – although in some cases, unfinished given the war outbreak.

- All staff hired must sign our IMPACT Initiatives and ACTED code of conduct and adhere to it, both in English and Arabic. Any proven break of the principles outlined, as well as other included principles on a project by project basis, will imply the suspension of the contract.

- All hired staff must submit a passport copy, or, in case expired, any sort of ID that can prove identity.

- IMPACT Initiatives does not hire members of the same family, with the exception of the gender inclusion in teams for the purpose of monitoring. In this case, female siblings, wifes, female cousins may be hired upon check of their suitability and background for the work. Independent salaries in this case are still paid for each of the individuals for the work performed.

- A formal vetting process is done upon hiring of each new staff. Candidates are security-screened twice by ACTED HQ both at the beginning of the selection process and before a formal job offer is issued in order to minimize the risk of hiring staff involved in terrorism activities. This vetting process is done in compliance with ACTED anti-terrorism .

- Certificates of completion of work are filled and signed at the end of each month for all monitors, as proof of work and as proof of their salary payslip.

- In case of non renewal of a contract, an evaluation form is filled by the field coordination, after discussion with the team leader in the respective governorate, to cancel the particular contract. Specific reasons on misconduct or wrongly work have to be outlined in the evaluation form.

IMPACT Initiatives follows an equal employment opportunity policy, based on the merit and qualifications of the staff in the Turkey / Jordan based offices, as well as anti-harassment and anti-discrimination policies that are intended to prosecute any moral or sexual harassment, or any type of discrimination.

Geographical coverage

IMPACT will monitor HMG Implementing Partners in two areas of Syria.

- North-West Syria: primary in the governorates of Idlib and Aleppo, and Hama. The locations have been discussed with HMG during the inception phase planning and will be discussed as well as at the beginning of each of the 6 month workplans.

- Southern Syria: mainly in the governorate of Dara’a and Rural Damascus

IMPACT will not cover any areas in Damascus, Government or ISIL controlled areas. Specific discussions on a case by case scenario will take place with HMG in case new locations are identified.

##### Work plan

Full work plan has been developed for this research cycle and it is attached in Annex 6.

- TIMELINE AND WORKPLANS

This programme will take place for two years and is broken down into four periods of six month workplans. The workplan included in this proposal outlines the timeline for the inception phase – six weeks – and the first six months. During the third party monitoring lifetime, there will be a total number of 434 man days of monitoring in 33 months.

Table 9 - Design and implementation of research and/or monitoring and evaluation (M&E) activities across the Syria HMG

|  |  | Months 0-8 | Months 9-14 | Months 15-20 | Months 21-26 | Months 27-33 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1 | Days allocated to monitoring visits | 94 | 85 | 85 | 85 | 85 |  |
|  | Output monitoring reports | 2 | to be defined | to be defined | to be defined | to be defined |  |
|  | Biannual outcome monitoring reports | 1 | 1 | 1 | 1 | 1 |  |
|  | Biannual progress report and presentation to the Syria CSSF Board | 1 | 1 | 1 | 1 | 1 |  |

Timeline

The overall programme is designed in the different phases outlined below.

| Phase 1 – Inception phase |  |
| --- | --- |
| June - July, 2016 | Inception Phase (2 months) |
| Phase 2 – Implementation phase |  |
| September– March , 2017 | Implementation of workplan 1 (7 months) |
| April - October, 2017 | Implementation of workplan 2 (6 months) |
| November , 2017 – April, 2018 | Implementation of workplan 3 (6 months) |
| May - September, 2018 | Implementation of workplan 4 (6 months) |
| October 2018 – March 2019 | Implementation of workplan 5 (6 months) |
| Phase 3 – Closure phase |  |
| April, 2019 | Closure of contract |

Before the beginning of a new monitoring phase, IMPACT will develop a detailed workplan outlining program activities (meeting with implementing partners, development or review of indicators, tools and protocols), monitoring activities (site visits for each implementing partners) and reporting activities (including output, outcome and progress reports) that will take place during each phase. In the framework of the inception phase, IMPACT has already developed such a plan for the first implementation phase (September 2016 -March 2017). The document is attached in Annex 6-7-8.

By the beginning of workplan 2, all the original projects will have been introduced into the monitoring programme. The Syria CSSF portfolio may also have changed by the start of workplan 2. Therefore projects in the monitoring programme will be reviewed in cooperation with HMG. For those projects undergoing a second wave of monitoring in workplan 2 and in further workplans, review meetings between HMG, IMPACT and the project implementing partner will take place to review the research questions, indicators, project activities and protocols.

# 8. Risks & Assumptions

Table 3: List of risks and mitigating action

| Risk | Mitigation Measure |
| --- | --- |
| Active conflict in areas where the activities are located impede access to the location for monitoring (medium/ high) | - Security monitoring and flexibility in the work plan - Allow for monitoring in the locations at different times |
| Conflict in areas where monitoring is scheduled delays the monitoring and present direct threats to staff in Syria (medium/ high) | - Security monitoring and flexibility in the work plan - Safety and security training for all monitors |
| Security / safety incidents in Turkey and Jordan impede normal implementation of the program (low) | - Security and safety plan is regularly revised to take into account potential developments. - Security and safety procedures are followed by the staff in all offices and areas of operation |
| Difficulties and / or delays in communication between the implementing partner field focal point and IMPACT staff (medium/ low) | - Planning during inception date on communication schedules and continuous follow up facilitate planning the monitoring visits on time - FCO team involvement in communication and follow up with the implementing partner |
| Discrepancies among the information received from partner and the field focal point in the services provided delay the monitoring process (low) | - Verification by IMPACT of the information provided by the implementing partners at early stages of the process assures correct location of services |
| Absence of IMPACT monitors in the specific location of the monitoring (low) | - IMPACT to discuss with FCO team potential alternatives for remote monitoring and other networks to join the monitoring |
| Lack of understanding from FCO partners of the objectives and goals of the third party monitoring (low) | - IMPACT and FCO will plan inception meetings with all partners involved - IMPACT will have open communication channels with the implementing partners during the monitoring process - Documents available for partners with the overview of the methodology and the objectives of Third Party Monitoring |
| Limited responses on household level surveys and other types of surveys (low) | - Clear explanation of goals and objectives of the surveys - Identification of alternative households and respondents to be interviewed following a same methodological procedure |
| Potential bias in the information collected by the monitors due to the limited number of sources (low) | - Combination of methodologies to collect different information that reflects different points of view - Assure the diversity of the informants, FGDs subjects, areas etc. |
| Lack of recognition and / or implementation of the monitoring activities (medium) | - Training on monitoring principles - Signature of principles and core values by project facilitators - Clear Standard Operational Procedures for field teams |
| Lack of technical project facilitators’ understanding of particular questions in a given assessment – monitoring by the field teams (low/ medium) | - Technical training and debriefings for each of the tools and monitoring types - Trainings implemented in Arabic, and all materials provided in Arabic - Standard monitoring tools are piloted before the full implementation - Continuous follow up with project facilitators during implementation |
| Gender bias in the information collected due to the lack of female monitors hired (medium/ low) | - Hiring policies adjusted to increment the likelihood to hire females. - Inclusion of female interviews as much as possible |

Table 4: List of key assumptions

Key assumptions

# Pre identified physically accessible locations remain accessible during the implementation of the programme. # Pre identified none physically accessible locations are accessible through alternative remote data collection methods. # Information about activities – when, where, and how- are made available to IMPACT on time to be able to carry out the monitoring. # Beneficiary lists and/or information about beneficiaries are made available ahead of time to collect data and monitor.

The Risk Log can be found in Annex 9.

# Monitoring and Evaluation

- Table 5: Monitoring and evaluation targets

| Objective | Indicator | Target overall program | Data collection methodology |
| --- | --- | --- | --- |
| HMG is informed about the TPM monitoring process, first workplan, budget, and tools | # of inception reports; | 1 | Output tracking |
| HMG is informed about each workplan | # of workplans each quarter | 5 | Output tracking |
| HMG is informed about the outcomes of its interventions | # of reports for outcome monitorings # of final reports # of minutes of bi-annual meetings | 1 per monitoring wave 5 5 | Output tracking |
| HMG is informed about the outputs of its interventions | # of reports for outcome monitoring | 1 per monitoring wave | Output tracking |
| HMG is provided with all data collected by TPM | # of aggregated database with collected data | 5 | Output tracking |
| HMG is satisfied with the monitoring process and its outcomes | # satisfaction surveys from HMG members involved and aware of the TPM process | At least 5 | Outcome tracking |
| IPs are satisfied with the monitoring process and its outcomes | # satisfaction surveys from IP focal points involved and aware of the TPM process | 8 | Outcome tracking |

# 10. Documentation Plan

Information will be stored in soft copies, and essential documents will be stored in hard copies in a folder which will be located in the IMPACT/REACH office in Antakya.

The hard copies stored will be:

- Donor Contract

- MOU IMPACT – ACTED

- TORs, including final tools, and relevant documents

- Meeting minutes, including KOM

- Reports

Additionally, the documents that will be produced in the framework of this program are:

- Inception report (1)

- Monitoring reports, per wave)

- Final report (5)

- Minutes of biannual meetings (5)

- Aggregated database with collected data (5)

- Sources of verification of monitoring activities (ns)

- Mapping of the locations of the monitoring and progress (ns)

# 11. Annexes

- Tamkeen Monitoring Matrix

- PCI Monitoring Matrix

- Taallum Monitoring Matrix

- SRM Indicator Template Matrix

- Data Management Plan

- Monitoring Workplan

- Development Workplan

- Reporting Workplan

- Risk Log

- Questionnaire/Tools

- RACI Matrix

- Budget

ANNEX 1: Tamkeen Monitoring matrix

ANNEX 2: PCI Monitoring matrix

ANNEX 3: Taallum Monitoring matrix

# ANNEX 4 : SRM Indicator Template

ANNEX 5: Data management plan

| Administrative Data |  |
| --- | --- |
| Project Name | Syria conflict, stability and security fund independent monitoring programme |
| Donor | HMG |
| Project Description |  | This Third Party Monitoring programme aims at ‘’performing a monitoring function on behalf of HMG to provide information that will assess the effective delivery of projects, contribute to improved project design, inform HMG-funded evaluations and support the evidence base of what works and what doesn’t work in this type of context’’. This program will monitor the interventions from at least six HMG partners in different locations inside Syria as part of eight HMG programs. |
| Project Data Contacts | Ana Garcia, Assessment Manager, Syria Crisis (ana.garcia@impact-initiatives.org) |
| DMP Version | Version 1 (8 July 2016) |
| Related Policies | Data management plan based on models and standards developed by the Digital Curation Centre (DCC), http://www.dcc.ac.uk, with overarching strategy drawn from the HMG core document on data management, record-keeping & monitoring, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/181176/HMGResearch-Open-and-Enhanced-Access-Policy.pdf. |
| Data Collection |  |
| What data will you collect or create? | - The monitoring process will aim at collecting data both on outputs and outcomes of Syria HMG Conflict, Security and Stability Fund (CSSF) programme. The output monitoring will collect data to verify that services and activities funded by HMG and implemented by its partners are being effectively delivered and received as planned. The outcome monitoring will collect data in order to better understand the outcomes of selected programmes implemented in specific locations. - Data collection tools will be designed in DOCX format and then stored as both DOCX and PDF files upon final validation from HMG. Each tool will be then translated into KoBo forms. - The data collected by the enumerators through KoBo will be exported each month to XLSX format and properly stored (see Storage and Backup section). - All information collected in qualitative text notes will be coded into categories to be able to analyse them in an Excel database. The coding categories will be defined by the Assessment Officer and reviewed by the Assessment Manager to ensure their relevance. - All data collected as part of the Third-Party Monitoring project will be original. For the purposes of spatial analysis, this data will be combined with pre-existing spatial data from OCHA and other sources. Each data source will be properly referenced. |
| How will the data be collected or created? | - Data will be collected through a combination of different qulitative methodologies, depending on the nature of the specific programme to be monitored, the information to be collected, and indicators to be measured. The methodologies will include Direct observation (DO), Key informant interviews (KIIs), as well as Focus Group Discussions (FGDs) and Area of Origin methodology (AoO) in particular cases. - Depending on the intervention to monitor, IMPACT will design appropriate monitoring based on a final validated list of indicators that is developed after reviewing the information corresponding to each of the programs to be monitored. For each of those indicators, questions will be developed. - IMPACT will lead the technical design of the indicators and tools, based on the project documents that HMG and each of the implementing partner will share with IMPACT during the inception phase. For each subsequent monitoring wave, IPs will be asked to submit updated programme documentation and meet with IMPACT to review the research questions and indicators in the orignal project monitoring matrix to determine where changes are required. IMPACT will then revise as appropriate, and revisions reviewed by the relevant HMG staff and the IP. - IMPACT will submit an initial draft of the indicators to HMG and the partners, and of the tools to HMG during the inception phase of the contract. Initial draft tools in English will be sent to HMG for feedback and inclusion of of additional information that is requested. In some cases, IMPACT will also ask IPs to review the language used in tools. IMPACT will compile all feedback and produce final versions of the tools in both English and Arabic which shall be signed off by HMG by the end of the inception phase (and in subsequent phases for projects being introduced into the programme beyond workplan 1A). - IMPACT staff will translate the questionnaires, which are checked after by the Field Assistant for a double check in language. After this, questionnaires are checked and reviewed by the Team leaders in Syria to make sure they are ready to be implemented for the pilot, with no mistakes, and no missing or contradictory information. - All tools that will be used are piloted by IMPACT at least two days before the full data collection is rolled out, both at office and field level, to make sure that the enumerators master the questionnaire and potential issues arise before the beginning of the data collection process. - For some projects, IMPACT and HMG will agree to conduct monitoring visits without setting a specific date in advance with the implementing partner. Other projects may require to set in advance a time and date for the visit. This will be determined as part of initial discussions in relation with each work plan and recorded in the individual project monitoring protocols. - One the methodology has been defined, appropriate tools developed and tested, as well as the location, day and time of the monitoring activity has been confirmed (if needed), IMPACT monitors will proceed with data collection. - Data collection process will be closely followed by the Field Coordinator and the Field Assistant. A master list for all HMG projects in the programmes will be created to track all the monitoring stages per each of the programs and per type of monitoring waves (outcome or output). Each of the monitoring is classified and labelled Ongoing, On Hold, or Security (if the activities are suspended for security reasons) and Cancelled. - The KOBO mobile data platform will be used for data collection where feasible through close-ended questionnaires. Observers will directly enter data into an encrypted, password-protected KoBo account via web browsers and the KoBoCollect mobile app. - Yet some type of monitoring and methodology, security conditions and the low adaptability of certain forms into KOBO, will require data collection to be done on paper forms. - When data collection will be done through paper questionnaires that will be handed over to the team leaders, who will scan all forms with their smartphone and send them to the Field Coordinator, who will insert all questionnaires into KOBO Collect server online. |
| How will the data be cleaned and triangulated? | - After each data collection session, monitors are debriefed first by the team leaders in each of the governorates where data collection has taken place. This first debriefing session will consist in reviewing the questionnaire and making sure all fields have been correctly filled in, and all notes for FGDs are comprehensive and clear. - Once this first check has taken place, the Database Officer and the Field Assistant, will proceed to check the information on the forms. They will identify any mismatching or strange information, and read through all of forms to make sure everything is correct and clear. When needed they will organize debriefing sessions on the phone and Skype with the monitors. - Part of this data check and data cleaning will include back translation in all cases where FGD are implemented. Once all qualitative information has been translated from the FGDs, sections of the information are back translated into Arabic one more time to make sure the information is accurate. Records of these back translations will be created to make sure the process is documented. - All information collected in the qualitative text notes will be coded into categories to be able to analyze them in an excel database. The coding categories will be defined by the Assessment Officer and reviewed by the Assessment Manager to ensure their relevance. - Data will be triangulated whenever a suspicion of flawless information, or lack of accuracy arise. Additionally, the Area of Origin network will be utilized to triangulate information collected in communities through other means, mainly for the outcome monitoring. This will be discussed along the project between HMG and IMPACT as the program evolves. - A confidence rating system will be applied to each individual variable when triangulating data from several AoO KI reporting on the same village, based on the level of expertise that each key informant type is expected to hold within the area of investigation where they have provided information. When presenting results at sub-district levels or above, the average confidence level of KIs reporting on each individual variable will be declared. - Reliability of data collected remotely will inevitably be lower than where direct data collection methods are used. To ensure data gathered through this exercise can be used as far as possible while accounting for varying degrees of reliability, two key measures are privileged as part of AoO. 1) Data is collected at the lowest possible administrative unit level, the village/neighbourhood level, to ensure that the area for which key informants are providing information corresponds directly to their actual area of knowledge, thereby mitigating unfounded deductions. 2) The level of coverage (proportion of villages assessed) will be declared for each variable when results are presented. - Following the cleaning process, the Database Officer will export clean in XLSX format. Each export will be digitally archived (see Storage and Backup). |
| Documentation and Metadata |  |
| What documentation and metadata will accompany the data? | - Metadata on the times of data entry and data export are automatically generated by KoBo for each data collection form submitted. - Other metadata for each data collection form submitted, including the name and code number of the enumerator, the event monitored, the date and place of monitoring, and preliminary information on KIs and FGD participants, will be manually entered into KoBo by the enumerators. - Data sets provided to HMG will be equipped with a “readme” tab detailing the contents of the file, overall information about the TPM project and any other information necessary to interpret the dataset. - As no one outside approved staff from IMPACT and HMG project teams will be permitted to access TPM data, there are no large-scale plans for systematic metadata creation for the benefit of outside users. Sharing the information will be subject to the confidentiality agreement signed between HMG and IMPACT. |
| Ethics and Legal Compliance |  |
| How will you manage any ethical issues? Note: Informed consent, anonymization, striking records, aggregation… | - To protect the anonymity of respondents, data will be accessible only by IMPACT and HMG staff members who have been previously granted access to the data. It will not be shared with any party outside these organizations or staff that does not have been granted with access - IMPACT will associate to each of the responders an anonymous code that will replace their names on the questionnaires and database. This will protect the basic personal information like names, job titles, age and gender of the KIs and FGD participants that will recorded by the monitors. No further personal information about these key informants will be collected or uploaded to KoBo. - Contact information for these KIs and FGD participants, which is necessary for the Field Coordinator to inform them of upcoming monitoring visits, will be recorded in a spreadsheet shared by email only with IMPACT and HMG staff members who are directly involved with TPM. This information will not be disseminated further under any circumstance. |
| How will you manage copyright and Intellectual Property Rights (IPR) issues? | - All data collected and analysed as part of the TPM project will be owned by HMG. All rights to this data are reserved to HMG. - No part of the TPM data or the analysis thereof will be shared, except internally with IMPACT and HMG staff members who are directly involved with the TPM project. No permission will be granted to any other party for the use or reuse of this data unless previously agreed by HMG. |
| Storage and Backup |  |
| How will the data be stored and backed up during the research? How will you manage access and security? | - All IMPACT staff laptops, mobile devices and email accounts will be password-protected, while personal laptops are not allowed for work as a general rule. - Collected data will be protected in the encrypted, password-protected account on KoBo. The password to this account will be provided only to IMPACT staff members who are working directly on the TPM programme. - Data will be exported on a monthly basis for backups on external drives, one in the field office and one in the Geneva HQ office. The database files will be encrypted and the encryption password shared only with IMPACT staff directly involved in the TPM program. - When collected on a paper form, the original data collection forms will be physically archived by IMPACT’s team leaders in Syria for a period of no more than three months. This period is necessary to allow the Field Coordinator and Database Officer to follow up on any anomalies in the reported data. At the end of two months, the team leaders will destroy the original forms to avoid undue risks. - IMPACT Turkey hosts the data temporarily on its server for the purpose of the analysis only. Once monitoring event is over, and data is validated, data will be stored in IMPACT HQ Geneva’s password-protected server, to which only specifically designated people based in Geneva office will have access. The data will be stored as a safe copy for HMG in case this is needed. The database files themselves will be encrypted and the encryption password shared only with IMPACT staff directly involved in the TPM program. Data will therefore be stored there until the end of the TPM, once all databases will be definitely transfer to HMG. - After the transfer to IMPACT HQ Geneva’s server, data will be erase both from IMPACT Turkey’s server and KoBo account. - IMPACT Turkey staff who will be in need to access this data will need to obtain a specific individual and time bound authorization, from Geneva IMPACT HQ officer in charge. No data will be retrieved without specific authorization. - IMPACT is in the process of securing a space on the server of the European Organization for Nuclear Research (CERN). As part of the REACH initiative (operated jointly with UNOSAT), IMPACT benefits from a dedicated space on the CERN server, which is highly protected against potential external cyber-attacks. Once this space is secured, all data will be store there, instead of on IMPACT HQ Geneva’s conventional server. |
| Selection and Preservation |  |
| Which data should be retained, shared, and/or preserved? | - All data archives will be retained indefinitely on IMPACT HQ Geneva’s password-protected server (on CERN’s one, once ready) and on an external hard drive, which is to be kept in a locked storage cabinet to which only specifically designated people based in Geneva office will have access. |
| What is the long-term preservation plan for the dataset? | - As all collected data will be retained indefinitely on IMPACT HQ Geneva’s server (on CERN’s one, once ready), there are no specific financial of logistics considerations which might impact the long‐term management of the data. |
| Data Sharing |  |
| How will you share the data? Are any restrictions on data sharing required? | - IMPACT will send to HMG on the raw data collected from all the regular monitoring exercises at the end of each monitoring cycle (every six months). The raw data will be organized into an aggregated Excel Sheet per program and separated per monitoring type - No part of the TPM data or the analysis thereof will be shared, except internally with IMPACT and HMG staff members who have been granted approval. - No permission will be granted to any other party for the use or reuse of this data. |
| Responsibilities |  |
| Who will be responsible for data management? | - The Assessment Officer will be responsible for creating, drafting and revising the data management plan, under the direct supervision of GIS Global Manager and Assessment Manager. He/she will also create data documentation and share data as needed with HMG and IMPACT Geneva HQ. - The Field Coordinator will be responsible for ensuring that data is consistently collected by IMPACT monitors through KoBo, as well as for communicating any relevant changes in data management policy to IMPACT monitors and team leaders. - When data is collected on paper forms, the Field Coordinator will ensure that the forms are properly scanned by IMPACT monitors, uploaded into regular KoBo forms and transferred to the Database Officer. - The Database Officer will be responsible for ensuring full staff compliance with the data management plan on a day-to-day basis, and particularly for maintaining the KoBo server and ensuring regular backups of all project files to an external drive. - Once the data analysis is completed, the Assessment Officer will be in charge of transferring all data to IMPACT Geneva HQ. - A specifically designated person at IMPACT Geneva HQ will be responsible to store data both on an external drive and on the office server (on the CERN’s one once ready). This person will also be in charge of giving specific individual and time bound authorization to IMPACT Turkey staff to retrieve data, if needed. - Once the transfer and storage in IMPACT Geneva is done, the Assessment Officer will be in charge of erasing data from KoBo and the IMPACT Turkey’s server. - The Assessment Manager will be responsible for negotiating any significant changes to the above data management plan or data sharing policies in close collaboration with HMG. - All staff members are responsible for password-protecting their laptops and mobile devices and keeping all account passwords confidential. |

Adapted from: DCC. (2013). Checklist for a Data Management Plan. v.4.0. Edinburgh: Digital Curation

Centre. Available online: http://www.dcc.ac.uk/resources/data-management-plans

ANNEX 6: Monitoring workplan

ANNEX 7: Development workplan

ANNEX 8: Reporting workplan

ANNEX 9: Risk log

# ANNEX 10: Questionnaire(s) / Tool(s)

Tools per program :

- Tamkeen; Implementing Partner: Adam Smith International (ASI)

      - Tool for FGD with Local Administrative Council (LAC) and Tamkeen Committee (TC)

      - Tool for FGD with representatives of local CSOs

      - Tool for FGD with representatives of local women CSOs

      - Tool for KII with for LAC members

      - Tool for KII with TC members

      - Tool for DO for LAC projects

- Aman Network Program; Implementing Partner Peacebuilding Initiative – CCSD

      - Tool for FGD with local community stakeholders

      - Tool for KII with local AN partners

      - Tool for KII with CCSD staff

      - Tool for KII with AN volunteers

- Taallum Program; Implementing Partner: Adam Smith International (ASI)

      - Tool for FGD with PED and EA representatives

      - Tool for KII with teachers and school leaders

      - Tool for KII with Taallum field staff

All tools can be found in the REACH Resource Centre.

# Annex 11: RACI Matrix

# Annex 12: Budget

The analysis framework is adapted from Krueger–Casey,Focus Group Discussions, 2009, Sage Publications

The original number of monitoring days for the first workplan was reduced in agreement with HMG to take into consideration the GBP devaluation

The frequency of reporting for the first workplan was reduced in agreement with HMG to take into consideration the GBP devaluation